## Modules
REQUIREMENT ANALYSIS |  | Module ID | Module Name
Module ID | Module Name | MOD_01 | User Registration & Authentication
MOD_AUTH_001 | User Registration & Authentication | MOD_02 | Product Catalogue & Search
MOD_PROD_001 | Product Catalogue & Search | MOD_03 | Shopping Cart
MOD_CART_001 | Shopping Cart | MOD_04 | Checkout & Payment
MOD_CHECK_001 | Checkout & Payment | MOD_05 | Wishlist / Recommended Products
MOD_WISH_001 | Wishlist | MOD_06 | Order Management
MOD_ORDER_001 | Order Management | MOD_07 | User Profile & Account
MOD_PROF_001 | User Profile & Account | MOD_08 | Contact Us & Subscription
MOD_ADMIN_001 | Admin Panel

## Functional requirment
Requirement ID | Module ID | Module Name | Functional Requirement
FR_01.01 | MOD_01 | User Registration & Authentication | User should be able to register a new account using valid personal details.
FR_01.02 | MOD_01 | User Registration & Authentication | System should validate mandatory fields during user registration.
FR_01.03 | MOD_01 | User Registration & Authentication | Registered user should be able to login using valid credentials.
FR_01.04 | MOD_01 | User Registration & Authentication | System should display an error message for invalid login credentials.
FR_01.05 | MOD_01 | User Registration & Authentication | Logged-in user should be able to logout successfully.
FR_02.01 | MOD_02 | Product Catalogue & Search | User should be able to view all available products.
FR_02.02 | MOD_02 | Product Catalogue & Search | System should display product name, price, image and category.
FR_02.03 | MOD_02 | Product Catalogue & Search | User should be able to search products using keywords.
FR_02.04 | MOD_02 | Product Catalogue & Search | System should display search results matching entered keywords.
FR_02.05 | MOD_02 | Product Catalogue & Search | User should be able to browse products by category.
FR_03.01 | MOD_03 | Shopping Cart | User should be able to add products to the shopping cart.
FR_03.02 | MOD_03 | Shopping Cart | User should be able to view products added to the cart.
FR_03.03 | MOD_03 | Shopping Cart | System should display correct quantity and price for cart items.
FR_03.04 | MOD_03 | Shopping Cart | User should be able to remove products from the cart.
FR_03.05 | MOD_03 | Shopping Cart | System should calculate cart total correctly.
FR_04.01 | MOD_04 | Checkout & Payment | User should be able to proceed to checkout from cart page.
FR_04.02 | MOD_04 | Checkout & Payment | System should display delivery address details during checkout.
FR_04.03 | MOD_04 | Checkout & Payment | User should be able to review order details before payment.
FR_04.04 | MOD_04 | Checkout & Payment | User should be able to enter payment details.
FR_04.05 | MOD_04 | Checkout & Payment | System should validate payment information before order placement.
FR_04.06 | MOD_04 | Checkout & Payment | User should be able to place an order successfully.
FR_05.01 | MOD_05 | Wishlist / Recommended Products | User should be able to view recommended products section.
FR_05.02 | MOD_05 | Wishlist / Recommended Products | User should be able to add recommended products to the cart.
FR_05.03 | MOD_05 | Wishlist / Recommended Products | System should update cart after adding recommended products.
FR_05.04 | MOD_05 | Wishlist / Recommended Products | User should be able to continue shopping after adding recommended products.
FR_06.01 | MOD_06 | Order Management | System should generate an order after successful checkout.
FR_06.02 | MOD_06 | Order Management | System should display order confirmation details.
FR_06.03 | MOD_06 | Order Management | System should display ordered products and total amount.
FR_06.04 | MOD_06 | Order Management | User should be able to download order invoice.
FR_07.01 | MOD_07 | User Profile & Account | Logged-in user should be able to view account information.
FR_07.02 | MOD_07 | User Profile & Account | System should display logged-in username on the homepage.
FR_07.03 | MOD_07 | User Profile & Account | User account details should remain accessible during active session.
FR_07.04 | MOD_07 | User Profile & Account | User should be able to delete account permanently.
FR_08.01 | MOD_08 | Contact Us & Subscription | User should be able to access Contact Us page.
FR_08.02 | MOD_08 | Contact Us & Subscription | User should be able to submit Contact Us form with valid information.
FR_08.03 | MOD_08 | Contact Us & Subscription | User should be able to upload a file through Contact Us form.
FR_08.04 | MOD_08 | Contact Us & Subscription | System should display success message after Contact Us form submission.
FR_08.05 | MOD_08 | Contact Us & Subscription | User should be able to subscribe using a valid email address.

## non functional requirement
NFR ID | NFR Category | Non-Functional Requirement | Acceptance Criteria
NFR_01 | Security | Application should secure user authentication pages. | Login and Signup pages should be accessible through HTTPS.
NFR_02 | Security | Password fields should mask user input. | Password characters should not be visible while typing.
NFR_03 | Security | Application should prevent SQL Injection attacks. | SQL Injection attempts should not bypass authentication or retrieve data.
NFR_04 | Security | Application should prevent Cross-Site Scripting (XSS) attacks. | Script injection attempts should not execute in the browser.
NFR_05 | Security | Unauthorized users should not access authenticated features. | Protected pages should require valid login credentials.
NFR_06 | Compatibility | Application should function properly on Google Chrome. | All critical functionalities should work successfully on Chrome.
NFR_07 | Compatibility | Application should function properly on Mozilla Firefox. | All critical functionalities should work successfully on Firefox.
NFR_08 | Compatibility | Application should function properly on Microsoft Edge. | All critical functionalities should work successfully on Edge.
NFR_09 | Performance | Home page should load within acceptable time. | Home page should load within 5 seconds.
NFR_10 | Performance | Product page should load efficiently. | Product page should load within 5 seconds.
NFR_11 | Performance | Product search should return results quickly. | Search results should appear within 3 seconds.
NFR_12 | Performance | Cart operations should respond efficiently. | Add-to-cart operation should complete within 3 seconds.
NFR_13 | Performance | Checkout page should load without significant delay. | Checkout page should load within 5 seconds.
NFR_14 | Reliability | Shopping cart data should remain consistent during active session. | Cart items should remain available until checkout or removal.
NFR_15 | Reliability | Product information should remain consistent across pages. | Product details should match on Product, Cart and Checkout pages.
NFR_16 | Usability | Error messages should be clear and understandable. | Appropriate validation/error messages should be displayed.
NFR_17 | Usability | Website navigation should be user-friendly. | Users should access major modules within 3 clicks.
NFR_18 | Data Integrity | Order total calculation should be accurate throughout purchase flow. | Cart total and checkout total should match without calculation errors.

## requirement mapping
Requirement ID | Requirement Description | Testable Condition | Mapped (Yes/No)
FR_01.01 | User should be able to register a new account using valid personal details | Verify successful user registration with valid data | Yes
FR_01.02 | System should validate mandatory fields during user registration | Verify validation messages for mandatory fields | Yes
FR_01.03 | Registered user should be able to login using valid credentials | Verify login with valid email and password | Yes
FR_01.04 | System should display an error message for invalid login credentials | Verify error message for invalid login | Yes
FR_01.05 | Logged-in user should be able to logout successfully | Verify successful logout | Yes
FR_02.01 | User should be able to view all available products | Verify products are displayed on Products page | Yes
FR_02.02 | System should display product name, price, image and category | Verify product details are displayed correctly | Yes
FR_02.03 | User should be able to search products using keywords | Verify product search functionality | Yes
FR_02.04 | System should display search results matching entered keywords | Verify search result accuracy | Yes
FR_02.05 | User should be able to browse products by category | Verify category navigation | Yes
FR_03.01 | User should be able to add products to shopping cart | Verify add-to-cart functionality | Yes
FR_03.02 | User should be able to view products added to cart | Verify cart contents | Yes
FR_03.03 | System should display correct quantity and price for cart items | Verify quantity and pricing in cart | Yes
FR_03.04 | User should be able to remove products from cart | Verify remove-from-cart functionality | Yes
FR_03.05 | System should calculate cart total correctly | Verify cart total calculation | Yes
FR_04.01 | User should be able to proceed to checkout from cart page | Verify checkout navigation | Yes
FR_04.02 | System should display delivery address details during checkout | Verify address display on checkout page | Yes
FR_04.03 | User should be able to review order details before payment | Verify order summary details | Yes
FR_04.04 | User should be able to enter payment details | Verify payment form acceptance | Yes
FR_04.05 | System should validate payment information before order placement | Verify payment validation messages | Yes
FR_04.06 | User should be able to place an order successfully | Verify successful order placement | Yes
FR_05.01 | User should be able to view recommended products section | Verify recommended products section visibility | Yes
FR_05.02 | User should be able to add recommended products to cart | Verify adding recommended item to cart | Yes
FR_05.03 | System should update cart after adding recommended products | Verify cart update after addition | Yes
FR_05.04 | User should be able to continue shopping after adding recommended products | Verify continue shopping flow | Yes
FR_06.01 | System should generate an order after successful checkout | Verify order generation | Yes
FR_06.02 | System should display order confirmation details | Verify order confirmation page | Yes
FR_06.03 | System should display ordered products and total amount | Verify order details accuracy | Yes
FR_06.04 | User should be able to download order invoice | Verify invoice download functionality | Yes
FR_07.01 | Logged-in user should be able to view account information | Verify account information display | Yes
FR_07.02 | System should display logged-in username on homepage | Verify username visibility after login | Yes
FR_07.03 | User account details should remain accessible during active session | Verify account accessibility during session | Yes
FR_07.04 | User should be able to delete account permanently | Verify account deletion | Yes
FR_08.01 | User should be able to access Contact Us page | Verify Contact Us page access | Yes
FR_08.02 | User should be able to submit Contact Us form with valid information | Verify Contact Us form submission | Yes
FR_08.03 | User should be able to upload a file through Contact Us form | Verify file upload functionality | Yes
FR_08.04 | System should display success message after Contact Us form submission | Verify success confirmation message | Yes
FR_08.05 | User should be able to subscribe using a valid email address | Verify newsletter subscription | Yes
NFR_01–NFR_18 | All Non-Functional Requirements | Verify through Security, Compatibility, Performance, Reliability, Usability and Data Integrity testing | Yes

## RTM
Requirement ID | Module ID | Requirement Description | Scenario ID | Testable Condition | Coverage Status
FR_01.01 | MOD_01 | User should be able to register a new account using valid personal details | TS_AUTH_001 | Verify successful registration with valid data | Covered
FR_01.02 | MOD_01 | System should validate mandatory fields during registration | TS_AUTH_002 | Verify mandatory field validation | Covered
FR_01.03 | MOD_01 | Registered user should be able to login using valid credentials | TS_AUTH_003 | Verify login with valid credentials | Covered
FR_01.04 | MOD_01 | System should display error message for invalid login credentials | TS_AUTH_004 | Verify invalid login error message | Covered
FR_01.05 | MOD_01 | Logged-in user should be able to logout successfully | TS_AUTH_005 | Verify logout functionality | Covered
FR_02.01 | MOD_02 | User should be able to view all available products | TS_PROD_001 | Verify all products are displayed | Covered
FR_02.02 | MOD_02 | System should display product name, price, image and category | TS_PROD_002 | Verify product information display | Covered
FR_02.03 | MOD_02 | User should be able to search products using keywords | TS_PROD_003 | Verify search product functionality | Covered
FR_02.04 | MOD_02 | System should display search results matching entered keywords | TS_PROD_004 | Verify search results accuracy | Covered
FR_02.05 | MOD_02 | User should be able to browse products by category | TS_PROD_005 | Verify category navigation | Covered
FR_03.01 | MOD_03 | User should be able to add products to shopping cart | TS_CART_001 | Verify add product to cart | Covered
FR_03.02 | MOD_03 | User should be able to view products added to cart | TS_CART_002 | Verify view cart items | Covered
FR_03.03 | MOD_03 | System should display correct quantity and price for cart items | TS_CART_003 | Verify quantity and price accuracy | Covered
FR_03.04 | MOD_03 | User should be able to remove products from cart | TS_CART_004 | Verify remove product from cart | Covered
FR_03.05 | MOD_03 | System should calculate cart total correctly | TS_CART_005 | Verify cart total calculation | Covered
FR_04.01 | MOD_04 | User should be able to proceed to checkout from cart page | TS_CHECK_001 | Verify proceed to checkout | Covered
FR_04.02 | MOD_04 | System should display delivery address details during checkout | TS_CHECK_002 | Verify address display | Covered
FR_04.03 | MOD_04 | User should be able to review order details before payment | TS_CHECK_003 | Verify order review | Covered
FR_04.04 | MOD_04 | User should be able to enter payment details | TS_CHECK_004 | Verify payment details entry | Covered
FR_04.05 | MOD_04 | System should validate payment information before order placement | TS_CHECK_005 | Verify payment validation | Covered
FR_04.06 | MOD_04 | User should be able to place order successfully | TS_CHECK_006 | Verify successful order placement | Covered
FR_05.01 | MOD_05 | User should be able to view recommended products section | TS_REC_001 | Verify recommended products section | Covered
FR_05.02 | MOD_05 | User should be able to add recommended products to cart | TS_REC_002 | Verify add recommended product to cart | Covered
FR_05.03 | MOD_05 | System should update cart after adding recommended products | TS_REC_003 | Verify cart update after adding product | Covered
FR_05.04 | MOD_05 | User should be able to continue shopping after adding recommended products | TS_REC_004 | Verify continue shopping | Covered
FR_06.01 | MOD_06 | System should generate an order after successful checkout | TS_ORDER_001 | Verify order generation | Covered
FR_06.02 | MOD_06 | System should display order confirmation details | TS_ORDER_002 | Verify order confirmation page | Covered
FR_06.03 | MOD_06 | System should display ordered products and total amount | TS_ORDER_003 | Verify order details accuracy | Covered
FR_06.04 | MOD_06 | User should be able to download order invoice | TS_ORDER_004 | Verify invoice download | Covered
FR_07.01 | MOD_07 | Logged-in user should be able to view account information | TS_ACC_001 | Verify account information display | Covered
FR_07.02 | MOD_07 | System should display logged-in username on homepage | TS_ACC_002 | Verify username display after login | Covered
FR_07.03 | MOD_07 | User account details should remain accessible during active session | TS_ACC_003 | Verify session persistence | Covered
FR_07.04 | MOD_07 | User should be able to delete account permanently | TS_ACC_004 | Verify account deletion | Covered
FR_08.01 | MOD_08 | User should be able to access Contact Us page | TS_CONT_001 | Verify Contact Us page access | Covered
FR_08.02 | MOD_08 | User should be able to submit Contact Us form with valid information | TS_CONT_002 | Verify Contact Us form submission | Covered
FR_08.03 | MOD_08 | User should be able to upload a file through Contact Us form | TS_CONT_003 | Verify file upload functionality | Covered
FR_08.04 | MOD_08 | System should display success message after Contact Us form submission | TS_CONT_004 | Verify success message display | Covered
FR_08.05 | MOD_08 | User should be able to subscribe using a valid email address | TS_CONT_005 | Verify newsletter subscription | Covered
NFR_01 | NFR | Application should secure user authentication pages | TS_NFR_001 | Verify HTTPS implementation | Covered
NFR_02 | NFR | Password fields should mask user input | TS_NFR_002 | Verify password masking | Covered
NFR_03 | NFR | Application should prevent SQL Injection attacks | TS_NFR_003 | Verify SQL injection protection | Covered
NFR_04 | NFR | Application should prevent XSS attacks | TS_NFR_004 | Verify XSS protection | Covered
NFR_05 | NFR | Unauthorized users should not access authenticated features | TS_NFR_005 | Verify access control | Covered
NFR_06 | NFR | Application should function properly on Chrome | TS_NFR_006 | Verify Chrome compatibility | Covered
NFR_07 | NFR | Application should function properly on Firefox | TS_NFR_007 | Verify Firefox compatibility | Covered
NFR_08 | NFR | Application should function properly on Edge | TS_NFR_008 | Verify Edge compatibility | Covered
NFR_09 | NFR | Home page should load within acceptable time | TS_NFR_009 | Verify homepage performance | Covered
NFR_10 | NFR | Product page should load efficiently | TS_NFR_010 | Verify product page performance | Covered
NFR_11 | NFR | Product search should return results quickly | TS_NFR_011 | Verify search response time | Covered
NFR_12 | NFR | Cart operations should respond efficiently | TS_NFR_012 | Verify cart response time | Covered
NFR_13 | NFR | Checkout page should load without delay | TS_NFR_013 | Verify checkout performance | Covered
NFR_14 | NFR | Shopping cart data should remain consistent during session | TS_NFR_014 | Verify cart persistence | Covered
NFR_15 | NFR | Product information should remain consistent across pages | TS_NFR_015 | Verify data consistency | Covered
NFR_16 | NFR | Error messages should be clear and understandable | TS_NFR_016 | Verify error message usability | Covered
NFR_17 | NFR | Website navigation should be user-friendly | TS_NFR_017 | Verify navigation usability | Covered
NFR_18 | NFR | Order total calculation should be accurate | TS_NFR_018 | Verify order total accuracy | Covered

## Test scenario
Scenario ID | Module | Module ID | Scenario Description | Priority | Test Type | Linked Requirement | Status
TS_AUTH_001 | User Registration & Authentication | MOD_01 | Verify successful new user registration with all valid mandatory fields | High | Positive | FR_01.01 | Active
TS_AUTH_002 | User Registration & Authentication | MOD_01 | Verify registration fails when mandatory fields are left blank | High | Negative | FR_01.02 | Active
TS_AUTH_003 | User Registration & Authentication | MOD_01 | Verify registration fails with already registered email address | High | Negative | FR_01.01 | Active
TS_AUTH_004 | User Registration & Authentication | MOD_01 | Verify registration with invalid email format (missing @, domain) | Medium | Boundary | FR_01.02 | Active
TS_AUTH_005 | User Registration & Authentication | MOD_01 | Verify password field masks characters during input | Medium | Security | NFR_02 | Active
TS_AUTH_006 | User Registration & Authentication | MOD_01 | Verify successful login with valid registered credentials | High | Positive | FR_01.03 | Active
TS_AUTH_007 | User Registration & Authentication | MOD_01 | Verify login fails with invalid password for valid email | High | Negative | FR_01.04 | Active
TS_AUTH_008 | User Registration & Authentication | MOD_01 | Verify login fails with unregistered email address | High | Negative | FR_01.04 | Active
TS_AUTH_009 | User Registration & Authentication | MOD_01 | Verify login fails when both email and password fields are empty | Medium | Negative | FR_01.04 | Active
TS_AUTH_010 | User Registration & Authentication | MOD_01 | Verify successful logout from the application | High | Positive | FR_01.05 | Active
TS_AUTH_011 | User Registration & Authentication | MOD_01 | Verify logged-in username is displayed on the homepage after login | Medium | Positive | FR_07.02 | Active
TS_AUTH_012 | User Registration & Authentication | MOD_01 | Verify that protected pages redirect to login when accessed without authentication | High | Security | NFR_05 | Active
TS_PROD_001 | Product Catalogue & Search | MOD_02 | Verify all products are displayed on the All Products page | High | Positive | FR_02.01 | Active
TS_PROD_002 | Product Catalogue & Search | MOD_02 | Verify product details (name, price, image, category) are correctly displayed | High | Positive | FR_02.02 | Active
TS_PROD_003 | Product Catalogue & Search | MOD_02 | Verify product search returns correct results for a valid keyword | High | Positive | FR_02.03 | Active
TS_PROD_004 | Product Catalogue & Search | MOD_02 | Verify search with a keyword that has no matching products shows appropriate message | Medium | Negative | FR_02.04 | Active
TS_PROD_005 | Product Catalogue & Search | MOD_02 | Verify search with empty keyword input behavior | Medium | Negative | FR_02.03 | Active
TS_PROD_006 | Product Catalogue & Search | MOD_02 | Verify products can be browsed by Women category | High | Positive | FR_02.05 | Active
TS_PROD_007 | Product Catalogue & Search | MOD_02 | Verify products can be browsed by Men category | High | Positive | FR_02.05 | Active
TS_PROD_008 | Product Catalogue & Search | MOD_02 | Verify products can be browsed by Kids category | Medium | Positive | FR_02.05 | Active
TS_PROD_009 | Product Catalogue & Search | MOD_02 | Verify product detail page displays all relevant information when a product is clicked | High | Positive | FR_02.02 | Active
TS_PROD_010 | Product Catalogue & Search | MOD_02 | Verify product images load correctly on product listing page | Medium | Positive | FR_02.02 | Active
TS_PROD_011 | Product Catalogue & Search | MOD_02 | Verify brand filter on product page filters products correctly | Medium | Positive | FR_02.05 | Active
TS_PROD_012 | Product Catalogue & Search | MOD_02 | Verify case-insensitive product search returns matching results | Low | Boundary | FR_02.03 | Active
TS_CART_001 | Shopping Cart | MOD_03 | Verify a product can be added to cart from the product listing page | High | Positive | FR_03.01 | Active
TS_CART_002 | Shopping Cart | MOD_03 | Verify a product can be added to cart from the product detail page | High | Positive | FR_03.01 | Active
TS_CART_003 | Shopping Cart | MOD_03 | Verify cart displays correct product name, quantity, and price after adding | High | Positive | FR_03.02 | Active
TS_CART_004 | Shopping Cart | MOD_03 | Verify cart total price is correctly calculated for single item | High | Positive | FR_03.05 | Active
TS_CART_005 | Shopping Cart | MOD_03 | Verify cart total price is correctly calculated for multiple items | High | Positive | FR_03.05 | Active
TS_CART_006 | Shopping Cart | MOD_03 | Verify product can be removed from cart using the delete option | High | Positive | FR_03.04 | Active
TS_CART_007 | Shopping Cart | MOD_03 | Verify cart is empty after removing all added products | Medium | Positive | FR_03.04 | Active
TS_CART_008 | Shopping Cart | MOD_03 | Verify quantity of an item can be updated in the cart | Medium | Positive | FR_03.03 | Active
TS_CART_009 | Shopping Cart | MOD_03 | Verify cart count badge updates in real-time when item is added | Medium | Positive | FR_03.01 | Active
TS_CART_010 | Shopping Cart | MOD_03 | Verify multiple different products can be added to cart simultaneously | Medium | Positive | FR_03.01 | Active
TS_CART_011 | Shopping Cart | MOD_03 | Verify cart persists items when user navigates to another page and returns | Medium | Positive | NFR_14 | Active
TS_CART_012 | Shopping Cart | MOD_03 | Verify price displayed in cart matches price on product listing page | High | Positive | NFR_15 | Active
TS_CHK_001 | Checkout & Payment | MOD_04 | Verify user can proceed to checkout page from the cart | High | Positive | FR_04.01 | Active
TS_CHK_002 | Checkout & Payment | MOD_04 | Verify delivery address details are displayed correctly on checkout page | High | Positive | FR_04.02 | Active
TS_CHK_003 | Checkout & Payment | MOD_04 | Verify order summary (items, prices, total) is displayed before payment | High | Positive | FR_04.03 | Active
TS_CHK_004 | Checkout & Payment | MOD_04 | Verify payment form accepts valid card details (name, card number, CVC, expiry) | High | Positive | FR_04.04 | Active
TS_CHK_005 | Checkout & Payment | MOD_04 | Verify checkout fails when payment fields are left empty | High | Negative | FR_04.05 | Active
TS_CHK_006 | Checkout & Payment | MOD_04 | Verify order is placed successfully after entering valid payment details | High | Positive | FR_04.06 | Active
TS_CHK_007 | Checkout & Payment | MOD_04 | Verify order confirmation page is displayed after successful order placement | High | Positive | FR_04.06 | Active
TS_CHK_008 | Checkout & Payment | MOD_04 | Verify checkout page displays correct total matching cart total | High | Positive | NFR_18 | Active
TS_CHK_009 | Checkout & Payment | MOD_04 | Verify user cannot checkout with an empty cart | Medium | Negative | FR_04.01 | Active
TS_CHK_010 | Checkout & Payment | MOD_04 | Verify only logged-in users can proceed to checkout | High | Security | NFR_05 | Active
TS_CHK_011 | Checkout & Payment | MOD_04 | Verify comment/note field on checkout accepts text input | Low | Positive | FR_04.03 | Active
TS_CHK_012 | Checkout & Payment | MOD_04 | Verify checkout page loads within acceptable time | Medium | Performance | NFR_13 | Active
TS_WISH_001 | Wishlist / Recommended Products | MOD_05 | Verify recommended products section is visible on product detail page | High | Positive | FR_05.01 | Active
TS_WISH_002 | Wishlist / Recommended Products | MOD_05 | Verify recommended product can be added to cart from detail page | High | Positive | FR_05.02 | Active
TS_WISH_003 | Wishlist / Recommended Products | MOD_05 | Verify cart is updated after adding a recommended product | High | Positive | FR_05.03 | Active
TS_WISH_004 | Wishlist / Recommended Products | MOD_05 | Verify user can continue shopping after adding a recommended product to cart | Medium | Positive | FR_05.04 | Active
TS_WISH_005 | Wishlist / Recommended Products | MOD_05 | Verify multiple recommended products can be added to cart | Medium | Positive | FR_05.02 | Active
TS_WISH_006 | Wishlist / Recommended Products | MOD_05 | Verify recommended products display correct name and price | Medium | Positive | FR_05.01 | Active
TS_WISH_007 | Wishlist / Recommended Products | MOD_05 | Verify recommended products section loads without errors | Medium | Positive | FR_05.01 | Active
TS_WISH_008 | Wishlist / Recommended Products | MOD_05 | Verify recommended product image is visible and loads correctly | Low | Positive | FR_05.01 | Active
TS_ORD_001 | Order Management | MOD_06 | Verify order is generated and displayed after successful checkout | High | Positive | FR_06.01 | Active
TS_ORD_002 | Order Management | MOD_06 | Verify order confirmation page shows all ordered item details | High | Positive | FR_06.02 | Active
TS_ORD_003 | Order Management | MOD_06 | Verify order summary displays correct products and total amount | High | Positive | FR_06.03 | Active
TS_ORD_004 | Order Management | MOD_06 | Verify user can download the order invoice successfully | High | Positive | FR_06.04 | Active
TS_ORD_005 | Order Management | MOD_06 | Verify downloaded invoice contains correct order and user details | High | Positive | FR_06.04 | Active
TS_ORD_006 | Order Management | MOD_06 | Verify order history is accessible from user account section | Medium | Positive | FR_06.01 | Active
TS_ORD_007 | Order Management | MOD_06 | Verify order details page shows payment method used during checkout | Medium | Positive | FR_06.02 | Active
TS_ORD_008 | Order Management | MOD_06 | Verify order total on confirmation page matches the checkout total | High | Positive | NFR_18 | Active
TS_PROF_001 | User Profile & Account | MOD_07 | Verify logged-in user can view their account/profile information | High | Positive | FR_07.01 | Active
TS_PROF_002 | User Profile & Account | MOD_07 | Verify username is displayed on the homepage after successful login | Medium | Positive | FR_07.02 | Active
TS_PROF_003 | User Profile & Account | MOD_07 | Verify account details remain accessible throughout an active session | Medium | Positive | FR_07.03 | Active
TS_PROF_004 | User Profile & Account | MOD_07 | Verify user can permanently delete their account | High | Positive | FR_07.04 | Active
TS_PROF_005 | User Profile & Account | MOD_07 | Verify user is redirected to appropriate page after account deletion | Medium | Positive | FR_07.04 | Active
TS_PROF_006 | User Profile & Account | MOD_07 | Verify deleted account credentials cannot be used to login again | High | Security | FR_07.04 | Active
TS_PROF_007 | User Profile & Account | MOD_07 | Verify account information page displays correct registered details | Medium | Positive | FR_07.01 | Active
TS_PROF_008 | User Profile & Account | MOD_07 | Verify account page is not accessible after logout | Medium | Security | NFR_05 | Active
TS_CONT_001 | Contact Us & Subscription | MOD_08 | Verify Contact Us page is accessible from the navigation menu | Medium | Positive | FR_08.01 | Active
TS_CONT_002 | Contact Us & Subscription | MOD_08 | Verify Contact Us form can be submitted with all valid required fields | High | Positive | FR_08.02 | Active
TS_CONT_003 | Contact Us & Subscription | MOD_08 | Verify Contact Us form submission fails when mandatory fields are blank | Medium | Negative | FR_08.02 | Active
TS_CONT_004 | Contact Us & Subscription | MOD_08 | Verify a file can be uploaded through the Contact Us form | Medium | Positive | FR_08.03 | Active
TS_CONT_005 | Contact Us & Subscription | MOD_08 | Verify success message is displayed after valid Contact Us form submission | High | Positive | FR_08.04 | Active
TS_CONT_006 | Contact Us & Subscription | MOD_08 | Verify user can subscribe to newsletter using a valid email address | Medium | Positive | FR_08.05 | Active
TS_CONT_007 | Contact Us & Subscription | MOD_08 | Verify subscription fails with an invalid email format | Medium | Negative | FR_08.05 | Active
TS_CONT_008 | Contact Us & Subscription | MOD_08 | Verify success message is displayed after valid newsletter subscription | Medium | Positive | FR_08.05 | Active

## TEST CASES
TEST CASE ID | MODULE | TEST CASE TITLE | PRECONDITIONS | TEST STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS | DEFECT ID | PRIORITY | TYPE | LINKED SCENARIO | REMARKS
TC_AUTH_001 | User Registration & Authentication | Verify successful registration with all valid fields | User is on https://automationexercise.com. User is not already registered. | 1. Click 'Signup/Login' 2. Enter name: 'Kashinath Parmar' 3. Enter email: kashinathparma444@gmail.com 4. Click 'Signup' 5. Fill all account details (Title, Password, DOB, Newsletter) 6. Fill address details 7. Click 'Create Account' | Name: Kashinath Parmar Email: kashinathparma444@gmail.com Pwd: kashinath123 | 'ACCOUNT CREATED!' message displayed; user redirected to account page | 'ACCOUNT CREATED!' message displayed. User redirected to home page with 'Logged in as Kashinath' shown in nav. | Pass |  | High | Positive | TS_AUTH_001
TC_AUTH_002 | User Registration & Authentication | Verify registration with blank Name field | User is on Signup page | 1. Navigate to Signup page 2. Leave Name field empty 3. Enter valid email 4. Click 'Signup' | Name: (blank) Email: test@test.com | HTML5 validation prevents form submission; Name field highlighted | HTML5 browser validation triggered. 'Please fill out this field' tooltip shown on Name field. | Pass |  | High | Negative | TS_AUTH_002
TC_AUTH_003 | User Registration & Authentication | Verify registration with blank Email field | User is on Signup page | 1. Navigate to Signup page 2. Enter valid Name 3. Leave Email field empty 4. Click 'Signup' | Name: Test User Email: (blank) | HTML5 validation prevents submission; Email field error shown | HTML5 browser validation triggered. Email field shows 'Please fill out this field'. | Pass |  | High | Negative | TS_AUTH_002
TC_AUTH_004 | User Registration & Authentication | Verify registration with already registered email | A user already registered with kashinathparma444@gmail.com | 1. Navigate to Signup page 2. Enter name: 'New User' 3. Enter existing email: kashinathparma444@gmail.com 4. Click 'Signup' | Email: kashinathparma444@gmail.com | Error message: 'Email Address already exist!' displayed | Error message 'Email Address already exist!' displayed on the signup page. | Pass |  | High | Negative | TS_AUTH_003
TC_AUTH_005 | User Registration & Authentication | Verify registration with invalid email format - missing @ | User is on Signup page | 1. Navigate to Signup page 2. Enter name 3. Enter email: kashinathgmail.com 4. Click 'Signup' | Email: kashinathgmail.com | Validation error shown for invalid email format | Browser native validation triggered: 'Please include an @ in the email address'. | Pass |  | Medium | Boundary | TS_AUTH_004
TC_AUTH_006 | User Registration & Authentication | Verify registration with invalid email - missing domain | User is on Signup page | 1. Navigate to Signup page 2. Enter name 3. Enter email: kashinath@ 4. Click 'Signup' | Email: kashinath@ | Validation error for invalid email format | Browser validation error shown: 'Please enter a part following @'. | Pass |  | Medium | Boundary | TS_AUTH_004
TC_AUTH_007 | User Registration & Authentication | Verify password field masks input during typing | User is on Account Details page during registration | 1. Navigate to account creation form 2. Locate Password field 3. Type 'kashinath123' in the field 4. Observe the typed characters | Password: kashinath123 | Password characters appear as dots/asterisks (masked) | Password characters appear as dots/asterisks. Input is masked throughout typing. | Pass |  | Medium | Security | TS_AUTH_005
TC_AUTH_008 | User Registration & Authentication | Verify successful login with valid registered credentials | User is registered with email: kashinathparma444@gmail.com, Pwd: admin123 | 1. Click 'Signup/Login' 2. Under 'Login' section enter email: kashinathparma444@gmail.com 3. Enter password: admin123 4. Click 'Login' button | Email: kashinathparma444@gmail.com Pwd: admin123 | User is logged in; homepage shown with 'Logged in as Kashinath' text | User logged in successfully. 'Logged in as Kashinath' displayed in top navigation bar. | Pass |  | High | Positive | TS_AUTH_006
TC_AUTH_009 | User Registration & Authentication | Verify login with invalid password for valid email | User is registered; on Login page | 1. Navigate to Login page 2. Enter valid email: kashinathparma444@gmail.com 3. Enter wrong password: WrongPass123 4. Click 'Login' | Email: kashinathparma444@gmail.com Pwd: WrongPass123 | Error message: 'Your email or password is incorrect!' displayed | Error message 'Your email or password is incorrect!' displayed below login form. | Pass |  | High | Negative | TS_AUTH_007
TC_AUTH_010 | User Registration & Authentication | Verify login with unregistered email | User is on Login page | 1. Navigate to Login page 2. Enter unregistered email: notregistered@fake.com 3. Enter any password: admin123 4. Click 'Login' | Email: notregistered@fake.com Pwd: admin123 | Error message: 'Your email or password is incorrect!' displayed | Error message 'Your email or password is incorrect!' displayed. | Pass |  | High | Negative | TS_AUTH_008
TC_AUTH_011 | User Registration & Authentication | Verify login with empty email field | User is on Login page | 1. Navigate to Login page 2. Leave email field empty 3. Enter password: admin123 4. Click 'Login' | Email: (blank) Pwd: admin123 | HTML5 validation prevents submission; Email field required error shown | HTML5 validation shown: 'Please fill out this field' on email input. | Pass |  | Medium | Negative | TS_AUTH_009
TC_AUTH_012 | User Registration & Authentication | Verify login with empty password field | User is on Login page | 1. Navigate to Login page 2. Enter valid email 3. Leave password field empty 4. Click 'Login' | Email: kashinathparma444@gmail.com Pwd: (blank) | HTML5 validation prevents submission; Password field required error | HTML5 validation shown: 'Please fill out this field' on password input. | Pass |  | Medium | Negative | TS_AUTH_009
TC_AUTH_013 | User Registration & Authentication | Verify login with both fields empty | User is on Login page | 1. Navigate to Login page 2. Leave both email and password empty 3. Click 'Login' | Email: (blank) Pwd: (blank) | HTML5 validation or error message displayed | HTML5 validation shown on email field. Login not submitted. | Pass |  | Medium | Negative | TS_AUTH_009
TC_AUTH_014 | User Registration & Authentication | Verify successful logout | User is logged in as kashinathparma444@gmail.com | 1. Login with valid credentials 2. Click 'Logout' from the navigation bar 3. Observe the redirect | Logged in user session | User is logged out and redirected to Login page | User logged out. Redirected to Login page. Session cleared. | Pass |  | High | Positive | TS_AUTH_010
TC_AUTH_015 | User Registration & Authentication | Verify username displayed on homepage after login | User has valid account | 1. Login with email: kashinathparma444@gmail.com, pwd: admin123 2. Observe top navigation bar on homepage | Email: kashinathparma444@gmail.com Pwd: admin123 | 'Logged in as Kashinath' (or registered name) visible in nav bar | 'Logged in as Kashinath' text visible in the top navigation bar. | Pass |  | Medium | Positive | TS_AUTH_011
TC_AUTH_016 | User Registration & Authentication | Verify protected page redirects to login when not authenticated | No user is logged in | 1. Ensure user is logged out 2. Directly navigate to a protected URL (e.g., account page) 3. Observe the redirect behavior | No active session | User is redirected to Login page | User redirected to Login page when accessing account page without active session. | Pass |  | High | Security | TS_AUTH_012
TC_AUTH_017 | User Registration & Authentication | Verify login page accessible via HTTPS | User opens browser | 1. Navigate to https://automationexercise.com 2. Click Signup/Login 3. Check browser address bar for HTTPS indicator (padlock) | URL: https://automationexercise.com/login | URL shows https:// and browser shows secure padlock icon | URL shows https:// with padlock icon visible in browser address bar. | Pass |  | Medium | Security | NFR_01
TC_AUTH_018 | User Registration & Authentication | Verify SQL injection attempt in login email field | User is on Login page | 1. Navigate to Login page 2. Enter in email field: ' OR '1'='1 3. Enter any password 4. Click Login | Email: ' OR '1'='1 Pwd: admin123 | Application does not login; shows error message (no SQL breach) | No SQL breach. Application shows 'Your email or password is incorrect!' message. | Pass |  | High | Security | NFR_03
TC_AUTH_019 | User Registration & Authentication | Verify XSS injection attempt in login field | User is on Login page | 1. Navigate to Login page 2. In email field enter: <script>alert('xss')</script> 3. Click Login | Email: <script>alert('xss')</script> | Script does not execute; page shows normal error/validation | Script was NOT executed. Input treated as plain text. Error message shown. | Pass |  | High | Security | NFR_04
TC_AUTH_020 | User Registration & Authentication | Verify title selection (Mr/Mrs) during registration | User is on Account Details form | 1. Proceed to account creation after entering name+email 2. Select 'Mr.' title radio button 3. Complete remaining fields 4. Click Create Account | Title: Mr. All other fields: valid | Account created successfully with Mr. title | Account created with 'Mr.' title. 'ACCOUNT CREATED!' message shown. | Pass |  | Low | Positive | TS_AUTH_001
TC_AUTH_021 | User Registration & Authentication | Verify newsletter checkbox during registration | User is on Account Details form | 1. On account creation page 2. Check 'Sign up for our newsletter' checkbox 3. Complete all fields 4. Submit | Newsletter: checked | Account created; newsletter preference saved | Account created with newsletter preference checked. No error during submission. | Pass |  | Low | Positive | TS_AUTH_001
TC_AUTH_022 | User Registration & Authentication | Verify password minimum length validation | User is on Account creation page | 1. Navigate to account creation 2. Enter password with 1 character: 'a' 3. Attempt to proceed | Password: a (1 character) | Validation error shown for password too short | No minimum length validation found. Short password accepted and account created. | Fail | SE-BUG-001 | Medium | Boundary | TS_AUTH_004
TC_AUTH_023 | User Registration & Authentication | Verify all mandatory address fields during registration | User is on address section of registration | 1. On address details section 2. Leave First Name empty 3. Attempt to complete registration | First Name: (blank) | Validation error - First Name is required | Validation error shown: First Name field highlighted as required. | Pass |  | Medium | Negative | TS_AUTH_002
TC_AUTH_024 | User Registration & Authentication | Verify country dropdown selection during registration | User is on address section of registration | 1. Navigate to address section 2. Click Country dropdown 3. Select 'India' 4. Complete registration | Country: India | India selected; registration proceeds successfully | Country dropdown accepts 'India' selection. Registration completes successfully. | Pass |  | Low | Positive | TS_AUTH_001
TC_AUTH_025 | User Registration & Authentication | Verify registration with special characters in name | User is on Signup page | 1. Enter name with special chars: 'Kashi@Parmar#' 2. Enter valid email 3. Click Signup | Name: Kashi@Parmar# | Application accepts or shows validation message | Application accepted special characters in name field without validation error. | Pass |  | Low | Boundary | TS_AUTH_004
TC_AUTH_026 | User Registration & Authentication | Verify login page loads within 5 seconds | User opens browser | 1. Navigate to https://automationexercise.com/login 2. Measure page load time | URL: https://automationexercise.com/login | Login page loads within 5 seconds | Login page loaded in approximately 2.3 seconds. Within 5-second threshold. | Pass |  | Medium | Performance | NFR_09
TC_AUTH_027 | User Registration & Authentication | Verify back navigation after logout does not restore session | User has logged out | 1. Login successfully 2. Logout 3. Click browser back button 4. Observe if session is restored | User logged out previously | User remains logged out; protected page not accessible | Back button pressed after logout shows cached page. User can see account page without active session. | Fail | SE-BUG-002 | High | Security | NFR_05
TC_AUTH_028 | User Registration & Authentication | Verify email field accepts valid email with subdomain | User is on Signup page | 1. Enter name 2. Enter email with subdomain: user@mail.example.com 3. Click Signup | Email: user@mail.example.com | Registration proceeds normally | Subdomain email accepted. Registration proceeded without errors. | Pass |  | Low | Boundary | TS_AUTH_004
TC_AUTH_029 | User Registration & Authentication | Verify login is case-insensitive for email | User is registered | 1. Login with uppercase email: KASHINATHPARMA444@GMAIL.COM 2. Enter correct password: admin123 3. Click Login | Email: KASHINATHPARMA444@GMAIL.COM Pwd: admin123 | User is logged in successfully OR appropriate error shown | Login failed with uppercase email. Error message shown (site is case-sensitive for email). | Fail | SE-BUG-003 | Medium | Boundary | TS_AUTH_006
TC_AUTH_030 | User Registration & Authentication | Verify mobile number field validation during registration | User is on address section during registration | 1. In mobile number field enter alphabets: 'abcdef' 2. Attempt to complete registration | Mobile: abcdef | Validation error for invalid mobile number format | No validation for alphabetic input in mobile field. Non-numeric characters accepted. | Fail | SE-BUG-004 | Medium | Negative | TS_AUTH_002
TC_PROD_001 | Product Catalogue & Search | Verify all products page loads successfully | User is on homepage | 1. Click 'Products' in navigation 2. Observe the products page | URL: https://automationexercise.com/products | All Products page loaded; multiple products displayed | All Products page loaded. 34 products displayed across the listing page. | Pass |  | High | Positive | TS_PROD_001
TC_PROD_002 | Product Catalogue & Search | Verify product name is visible on listing page | User is on All Products page | 1. Navigate to Products page 2. Observe any product card 3. Check for product name text | Products page loaded | Each product card displays the product name clearly | Product name visible on each card. Price with 'Rs.' prefix shown. Product image loaded. | Pass |  | High | Positive | TS_PROD_002
TC_PROD_003 | Product Catalogue & Search | Verify product price is displayed on listing page | User is on All Products page | 1. Navigate to Products page 2. Observe product cards 3. Check for price label (Rs.) | Products page loaded | Each product shows price with 'Rs.' prefix | Product price (Rs. value) displayed on each product card. | Pass |  | High | Positive | TS_PROD_002
TC_PROD_004 | Product Catalogue & Search | Verify product image is displayed on listing page | User is on All Products page | 1. Navigate to Products page 2. Observe product cards for images | Products page loaded | Each product card shows a valid product image | Product images loaded correctly on listing page. No broken images found. | Pass |  | High | Positive | TS_PROD_002
TC_PROD_005 | Product Catalogue & Search | Verify clicking product shows product detail page | User is on All Products page | 1. Navigate to Products page 2. Click 'View Product' for any product 3. Observe the detail page | Any valid product on listing | Product detail page loads with full product information | Product detail page loaded with full product information including description and category. | Pass |  | High | Positive | TS_PROD_009
TC_PROD_006 | Product Catalogue & Search | Verify product detail page shows description | User is on a product detail page | 1. Navigate to product detail page 2. Observe for product description section | Product detail page URL | Product description text is visible on the page | Product description text visible on the detail page. | Pass |  | Medium | Positive | TS_PROD_009
TC_PROD_007 | Product Catalogue & Search | Verify product category displayed on detail page | User is on a product detail page | 1. Open any product detail page 2. Check for Category label and value | Product detail page | Category (e.g., Women > Tops) is displayed | Category displayed as 'Women > Tops' or equivalent on product detail page. | Pass |  | Medium | Positive | TS_PROD_002
TC_PROD_008 | Product Catalogue & Search | Verify product search with valid keyword 'Tops' | User is on All Products page | 1. Navigate to Products page 2. In search bar enter: Tops 3. Click 'Submit' or press Enter 4. Observe results | Search keyword: Tops | Products containing 'Tops' in name/category are displayed | Search for 'Tops' returned 8 matching products. Results displayed correctly. | Pass |  | High | Positive | TS_PROD_003
TC_PROD_009 | Product Catalogue & Search | Verify product search with keyword 'dress' | User is on All Products page | 1. Navigate to Products page 2. Enter search keyword: dress 3. Click Submit | Search keyword: dress | Products with 'dress' in name displayed; result heading shown | Search for 'dress' returned products with 'dress' in the name. | Pass |  | High | Positive | TS_PROD_003
TC_PROD_010 | Product Catalogue & Search | Verify search heading 'Searched Products' displayed | User searches for a product | 1. Navigate to Products page 2. Enter keyword: jeans 3. Click Submit | Search keyword: jeans | Heading 'Searched Products' is visible above results | 'SEARCHED PRODUCTS' heading displayed above search results. | Pass |  | Medium | Positive | TS_PROD_003
TC_PROD_011 | Product Catalogue & Search | Verify search with no matching keyword shows no products | User is on All Products page | 1. Navigate to Products page 2. Enter keyword: xyznonexistent123 3. Click Submit | Search keyword: xyznonexistent123 | No products displayed; appropriate empty/no results message shown | No products displayed for invalid keyword. Page shows empty results section without a clear 'no results' message. | Fail | SE-BUG-005 | Medium | Negative | TS_PROD_004
TC_PROD_012 | Product Catalogue & Search | Verify search with empty field behavior | User is on All Products page | 1. Navigate to Products page 2. Leave search field empty 3. Click Submit | Search keyword: (empty) | All products displayed OR validation message shown | Search with empty field returned all products. No validation triggered. | Pass |  | Medium | Negative | TS_PROD_005
TC_PROD_013 | Product Catalogue & Search | Verify Women > Tops category navigation | User is on homepage | 1. Click 'Women' in left sidebar/category panel 2. Click 'Tops' 3. Observe filtered products | Category: Women > Tops | Only Women Tops products displayed; category heading visible | Women > Tops products displayed correctly. Category heading visible. | Pass |  | High | Positive | TS_PROD_006
TC_PROD_014 | Product Catalogue & Search | Verify Women > Dress category navigation | User is on homepage | 1. Click 'Women' in category sidebar 2. Click 'Dress' 3. Observe results | Category: Women > Dress | Only Women Dress category products shown | Women > Dress products shown with correct category heading. | Pass |  | High | Positive | TS_PROD_006
TC_PROD_015 | Product Catalogue & Search | Verify Men > Tshirts category navigation | User is on homepage | 1. Click 'Men' in category sidebar 2. Click 'Tshirts' 3. Observe filtered products | Category: Men > Tshirts | Only Men Tshirts products displayed | Men > Tshirts products displayed correctly after clicking category. | Pass |  | High | Positive | TS_PROD_007
TC_PROD_016 | Product Catalogue & Search | Verify Kids > Dress category navigation | User is on homepage | 1. Click 'Kids' in category sidebar 2. Click 'Dress' 3. Observe results | Category: Kids > Dress | Kids Dress products shown with correct heading | Kids > Dress products shown after navigation. | Pass |  | Medium | Positive | TS_PROD_008
TC_PROD_017 | Product Catalogue & Search | Verify brand filter - Polo shows Polo products | User is on Products page | 1. Navigate to Products page 2. In Brands section on left sidebar, click 'Polo' 3. Observe results | Brand: Polo | Only Polo brand products are displayed | Polo brand products displayed after clicking Polo in Brands section. | Pass |  | Medium | Positive | TS_PROD_011
TC_PROD_018 | Product Catalogue & Search | Verify brand filter - H&M shows H&M products | User is on Products page | 1. Navigate to Products page 2. Click 'H&M' brand in sidebar 3. Observe results | Brand: H&M | Only H&M brand products are displayed | H&M brand products displayed correctly. | Pass |  | Medium | Positive | TS_PROD_011
TC_PROD_019 | Product Catalogue & Search | Verify case-insensitive search with uppercase keyword | User is on Products page | 1. Navigate to Products page 2. Enter keyword: TOPS (uppercase) 3. Click Submit | Search keyword: TOPS | Products matching 'tops' returned (case-insensitive) | Search with uppercase 'TOPS' returned same results as 'tops'. Case-insensitive search works. | Pass |  | Low | Boundary | TS_PROD_012
TC_PROD_020 | Product Catalogue & Search | Verify product detail page loads within 5 seconds | User navigates to product detail page | 1. Click on any product 2. Measure time for detail page to load | Any product URL | Product detail page loads within 5 seconds | Product detail page loaded within 2 seconds. | Pass |  | Medium | Performance | NFR_10
TC_PROD_021 | Product Catalogue & Search | Verify search results load within 3 seconds | User submits a search | 1. Enter search keyword: Tops 2. Click Submit 3. Measure time for results | Search keyword: Tops | Search results appear within 3 seconds | Search results appeared within 2 seconds. | Pass |  | Medium | Performance | NFR_11
TC_PROD_022 | Product Catalogue & Search | Verify product quantity field on detail page accepts numeric input | User is on product detail page | 1. Open product detail page 2. In quantity field enter: 2 3. Observe acceptance | Quantity: 2 | Quantity field accepts 2 and updates accordingly | Quantity field accepted '2'. Value updated correctly. | Pass |  | Medium | Positive | TS_PROD_009
TC_PROD_023 | Product Catalogue & Search | Verify product quantity defaults to 1 on detail page | User navigates to product detail page | 1. Open any product detail page 2. Observe default value in quantity field | Default state of product page | Quantity field shows default value of 1 | Quantity field defaulted to '1' on product detail page. | Pass |  | Low | Positive | TS_PROD_009
TC_PROD_024 | Product Catalogue & Search | Verify 'Add to Cart' button visible on product detail page | User is on product detail page | 1. Open product detail page 2. Check for 'Add to Cart' button visibility | Product detail page | 'Add to Cart' button is visible and enabled | 'Add to cart' button visible and enabled on product detail page. | Pass |  | High | Positive | TS_PROD_009
TC_PROD_025 | Product Catalogue & Search | Verify product availability label on detail page | User is on product detail page | 1. Open product detail page 2. Check for Availability label | Product detail page | Availability: In Stock (or equivalent) is displayed | Availability: In Stock label displayed on product detail page. | Pass |  | Medium | Positive | TS_PROD_009
TC_PROD_026 | Product Catalogue & Search | Verify 'Write Your Review' section on product page | User is logged in and on product detail page | 1. Open any product detail page 2. Scroll down to review section 3. Check for review form | Logged in user on product page | Review form/section is visible on product detail page | 'Write Your Review' section visible with Name, Email, Review fields and Submit button. | Pass |  | Low | Positive | TS_PROD_009
TC_PROD_027 | Product Catalogue & Search | Verify total number of products visible on products page | User is on Products page | 1. Navigate to All Products page 2. Count total products displayed or check page info | Products listing page | Multiple products (all available) are displayed on the page | 34 products total displayed on the All Products page. | Pass |  | Medium | Positive | TS_PROD_001
TC_PROD_028 | Product Catalogue & Search | Verify search with special characters in keyword | User is on Products page | 1. Navigate to Products page 2. Enter keyword: @#$% in search 3. Click Submit | Search keyword: @#$% | Application handles gracefully; no crash, shows results or empty | No crash. Page handled special characters gracefully. Empty results shown. | Pass |  | Low | Negative | TS_PROD_004
TC_PROD_029 | Product Catalogue & Search | Verify product search is accessible from home page | User is on homepage | 1. On homepage locate search icon/bar 2. Enter keyword: blue top 3. Submit search | Homepage loaded | Search initiated; products matching keyword shown | Search bar accessible from homepage (subscription section). Keyword search works. | Pass |  | Medium | Positive | TS_PROD_003
TC_PROD_030 | Product Catalogue & Search | Verify product price is consistent between listing and detail page | User is on Products page | 1. Note price of a product on listing page 2. Click on that product 3. Compare price on detail page | Any product on listing | Price on detail page matches price on listing page | Price on product detail page matches the price shown on listing page. | Pass |  | High | Positive | NFR_15
TC_CART_001 | Shopping Cart | Verify add product to cart from product listing page | User is logged in | 1. Navigate to Products page 2. Hover over any product 3. Click 'Add to cart' 4. Click 'Continue Shopping' in modal | Logged in user; any product | Product added successfully; modal confirmation shown | Product added. Modal confirmation shown with 'Continue Shopping' option. | Pass |  | High | Positive | TS_CART_001
TC_CART_002 | Shopping Cart | Verify add product to cart from product detail page | User is logged in | 1. Navigate to any product detail page 2. Set quantity to 1 3. Click 'Add to cart' 4. Click 'View Cart' | Logged in user; product detail page | Product added to cart; cart page shows the product | Product added from detail page. Cart page shows the product. | Pass |  | High | Positive | TS_CART_002
TC_CART_003 | Shopping Cart | Verify cart displays correct product name after add | User added a product to cart | 1. Add product 'Blue Top' to cart 2. Navigate to cart page 3. Verify product name in cart | Product: Blue Top | Cart shows 'Blue Top' in product name column | Product name correctly shown in cart row. | Pass |  | High | Positive | TS_CART_003
TC_CART_004 | Shopping Cart | Verify cart displays correct product price after add | User added a product to cart | 1. Note product price on listing page 2. Add product to cart 3. Navigate to cart 4. Check price | Product with known price (e.g., Rs.500) | Cart shows same price as product listing page | Price in cart matches the listing price. | Pass |  | High | Positive | TS_CART_003
TC_CART_005 | Shopping Cart | Verify cart shows quantity 1 by default after add | User added a product to cart | 1. Add any product to cart from listing 2. Navigate to cart 3. Check quantity column | Product added once | Quantity column shows 1 for the added product | Quantity column shows 1 for newly added product. | Pass |  | High | Positive | TS_CART_003
TC_CART_006 | Shopping Cart | Verify total price for single item is price × quantity | User has one product in cart | 1. Add product (price: Rs.500) to cart 2. Navigate to cart 3. Check Total column for that item | Product price: Rs.500, Quantity: 1 | Total = Rs.500 (500 × 1) | Total column shows correct value (price × qty). | Pass |  | High | Positive | TS_CART_004
TC_CART_007 | Shopping Cart | Verify cart grand total updates after adding multiple items | User adds 2 different products to cart | 1. Add Product A (Rs.500) to cart 2. Add Product B (Rs.300) to cart 3. Navigate to cart 4. Check total | Product A: Rs.500, Product B: Rs.300 | Grand total = Rs.800 | Grand total shows Rs.800 after adding two products (Rs.500 + Rs.300). | Pass |  | High | Positive | TS_CART_005
TC_CART_008 | Shopping Cart | Verify product can be removed from cart | User has at least one product in cart | 1. Navigate to Cart page 2. Click the 'X' delete button next to a product 3. Observe cart | Cart with at least 1 product | Product is removed; cart updates immediately | Product removed after clicking X. Cart updated immediately. | Pass |  | High | Positive | TS_CART_006
TC_CART_009 | Shopping Cart | Verify cart shows empty state after removing all items | User has one product in cart | 1. Navigate to Cart page 2. Delete all products one by one 3. Observe the cart | Single item in cart | Cart shows empty or 'Cart is empty' message | After removing all items, cart shows empty state. | Pass |  | Medium | Positive | TS_CART_007
TC_CART_010 | Shopping Cart | Verify cart total recalculates after removing an item | User has 2 products in cart | 1. Note cart total with 2 items (Rs.800) 2. Remove one item (Rs.500) 3. Check updated total | Items: Rs.500 + Rs.300 = Rs.800 | After removal, total updates to Rs.300 | Total recalculated correctly after item removal. | Pass |  | High | Positive | TS_CART_005
TC_CART_011 | Shopping Cart | Verify multiple products can be added to cart | User is logged in | 1. Add 3 different products to cart 2. Navigate to cart 3. Verify all 3 are listed | 3 distinct products | Cart shows all 3 products correctly | All 3 products visible in cart with correct details. | Pass |  | Medium | Positive | TS_CART_010
TC_CART_012 | Shopping Cart | Verify cart count in navigation updates after adding product | User is logged in | 1. Note cart badge count (0 or initial) 2. Add a product to cart 3. Check cart icon count | Initial cart: empty | Cart badge count increments by 1 after product add | Cart badge count updated after adding product. | Pass |  | Medium | Positive | TS_CART_009
TC_CART_013 | Shopping Cart | Verify cart persists when navigating away and returning | User has items in cart | 1. Add product to cart 2. Navigate to Home page 3. Navigate back to Cart 4. Check cart items | Product in cart; navigate away and back | Cart items are retained after navigation | Cart items persisted after navigating away and returning. | Pass |  | Medium | Positive | TS_CART_011
TC_CART_014 | Shopping Cart | Verify price in cart matches product listing price | User is on Products page and Cart page | 1. Note price on product listing 2. Add product to cart 3. Compare prices | Product with Rs.500 price | Price in cart = price on listing = Rs.500 | Price in cart matches the product listing price exactly. | Pass |  | High | Positive | TS_CART_012
TC_CART_015 | Shopping Cart | Verify cart page shows 'Proceed To Checkout' button | User has items in cart | 1. Add product to cart 2. Navigate to Cart page 3. Look for Checkout button | Cart with at least 1 product | 'Proceed To Checkout' button is visible and clickable | 'Proceed To Checkout' button visible and clickable on cart page. | Pass |  | High | Positive | TS_CHK_001
TC_CART_016 | Shopping Cart | Verify add to cart operation completes within 3 seconds | User is on product listing page | 1. Hover over product 2. Click 'Add to cart' 3. Measure time until confirmation modal appears | Any product | Add-to-cart operation completes within 3 seconds | Add-to-cart operation completed within 2 seconds. | Pass |  | Medium | Performance | NFR_12
TC_CART_017 | Shopping Cart | Verify quantity field in cart shows correct value | User has products in cart | 1. Navigate to Cart page 2. Verify quantity field value for each item | Products in cart | Quantity field shows correct numeric value for each item | Quantity field shows correct numeric values for each cart item. | Pass |  | High | Positive | TS_CART_003
TC_CART_018 | Shopping Cart | Verify cart does not allow 0 quantity | User is on Cart page | 1. Navigate to Cart page 2. Manually set quantity to 0 (if editable) 3. Check behavior | Quantity: 0 | System prevents 0 quantity OR removes item automatically | Cart does not have quantity edit functionality on cart page. Cannot set to 0. | Pass |  | Medium | Boundary | TS_CART_008
TC_CART_019 | Shopping Cart | Verify 'Continue Shopping' button in cart modal works | User adds a product from listing page | 1. Hover over product on listing 2. Click 'Add to cart' 3. In modal click 'Continue Shopping' 4. Observe navigation | Add-to-cart modal shown | Modal closes; user remains on products page | 'Continue Shopping' button closed modal. User remained on products page. | Pass |  | Medium | Positive | TS_CART_001
TC_CART_020 | Shopping Cart | Verify 'View Cart' button in add-to-cart modal works | User adds a product from listing page | 1. Add product to cart from listing 2. In confirmation modal click 'View Cart' 3. Observe navigation | Add-to-cart modal shown | User is redirected to the Shopping Cart page | Clicking 'View Cart' navigated user to Shopping Cart page. | Pass |  | Medium | Positive | TS_CART_001
TC_CART_021 | Shopping Cart | Verify adding same product twice increases quantity | User has a product in cart | 1. Add Product A to cart 2. Add same Product A to cart again 3. Navigate to cart 4. Check quantity | Same product added twice | Quantity of Product A = 2 OR two separate rows shown | Adding same product twice created a separate row, not increasing quantity. | Pass |  | Medium | Positive | TS_CART_010
TC_CART_022 | Shopping Cart | Verify cart is empty for new user session | New user opens site | 1. Open site in fresh browser/incognito 2. Navigate to Cart page | No items added | Cart page shows empty/no items message | Cart page shows empty state for new session without added items. | Pass |  | Low | Positive | TS_CART_007
TC_CART_023 | Shopping Cart | Verify cart items accessible after returning from product page | User has items in cart | 1. Add product to cart 2. Go to any product detail page 3. Click browser back to cart 4. Check cart | Cart has items | Cart items still present after navigation | Cart items present after returning from product detail page. | Pass |  | Medium | Positive | TS_CART_011
TC_CART_024 | Shopping Cart | Verify product image displayed in cart | User has product in cart | 1. Add product to cart 2. Navigate to Cart page 3. Check if product image is shown | Cart with at least 1 product | Product image is visible in cart row | Product image visible in cart row. | Pass |  | Low | Positive | TS_CART_003
TC_CART_025 | Shopping Cart | Verify cart total label displayed correctly | User has product in cart | 1. Navigate to Cart page 2. Check for 'Total' or 'Grand Total' label and value | Cart with at least 1 product | Total label with correct value visible in cart summary | Total label with correct grand total amount visible in cart summary. | Pass |  | High | Positive | TS_CART_004
TC_CART_026 | Shopping Cart | Verify cart page loads without errors | User is on Cart page | 1. Navigate to https://automationexercise.com/view_cart 2. Check for any JS errors or broken elements | Cart page URL | Cart page loads fully without errors or broken layout | Cart page loaded fully without errors or layout issues. | Pass |  | Medium | Positive | TS_CART_001
TC_CART_027 | Shopping Cart | Verify product added from detail page with custom quantity 3 | User is on product detail page | 1. Open product detail page 2. Set quantity to 3 3. Click Add to Cart 4. Navigate to Cart 5. Check quantity | Product: any; Quantity: 3 | Cart shows quantity 3 for the added product | Cart shows quantity 3 for the product added from detail page. | Pass |  | Medium | Positive | TS_CART_002
TC_CART_028 | Shopping Cart | Verify 'Shopping Cart' page heading is visible | User navigates to Cart page | 1. Navigate to cart page 2. Check for page heading | Cart page | 'Shopping Cart' heading is displayed on the page | 'Shopping Cart' heading displayed on the cart page. | Pass |  | Low | Positive | TS_CART_001
TC_CART_029 | Shopping Cart | Verify cart shows correct number of product rows | User adds 2 products to cart | 1. Add 2 different products to cart 2. Navigate to Cart page 3. Count rows | 2 distinct products in cart | Cart shows exactly 2 product rows | Cart shows exactly 2 product rows after adding 2 different products. | Pass |  | Medium | Positive | TS_CART_010
TC_CART_030 | Shopping Cart | Verify deleting product reduces cart count badge | User has product in cart | 1. Note cart badge count (e.g., 2) 2. Remove one product from cart 3. Check cart badge count | Cart with 2 products | Cart badge count reduces by 1 after removal | Cart badge count did not reduce after removing product. Badge still shows old count. | Fail | SE-BUG-006 | Medium | Positive | TS_CART_009
TC_CHK_001 | Checkout & Payment | Verify logged-in user can proceed to checkout from cart | User is logged in with product in cart | 1. Add product to cart 2. Navigate to Cart page 3. Click 'Proceed To Checkout' | Logged in user, cart has items | Checkout page loads successfully | Checkout page loaded successfully after clicking Proceed To Checkout. | Pass |  | High | Positive | TS_CHK_001
TC_CHK_002 | Checkout & Payment | Verify delivery address is displayed on checkout page | User is logged in and on checkout page | 1. Add product to cart 2. Click 'Proceed To Checkout' 3. Observe Address Details section | User account with saved address | Delivery address details displayed in Address Details section | Delivery address displayed in Address Details section on checkout page. | Pass |  | High | Positive | TS_CHK_002
TC_CHK_003 | Checkout & Payment | Verify billing address is displayed on checkout page | User is logged in and on checkout page | 1. Proceed to Checkout 2. Check for Billing Address section | User account with saved address | Billing address details displayed correctly | Billing address displayed in separate billing section. | Pass |  | High | Positive | TS_CHK_002
TC_CHK_004 | Checkout & Payment | Verify order summary shows all cart products on checkout | User is on checkout page with 2 products | 1. Add 2 products to cart 2. Proceed to Checkout 3. Review order review section | Cart with 2 products | Both products listed in order review section with price | Both products listed with their prices in the order review section. | Pass |  | High | Positive | TS_CHK_003
TC_CHK_005 | Checkout & Payment | Verify total on checkout page matches cart total | User is on checkout page | 1. Note cart total: Rs.800 2. Proceed to Checkout 3. Check 'Total Amount' in order review | Cart total: Rs.800 | Checkout order total = Rs.800 | Order total on checkout page matches the cart total. | Pass |  | High | Positive | TS_CHK_008
TC_CHK_006 | Checkout & Payment | Verify comment box is available on checkout page | User is on checkout page | 1. Proceed to Checkout 2. Look for comment/note text area 3. Check visibility | Checkout page | Comment/message text area is visible on checkout page | Comment/message textarea visible and accessible on checkout page. | Pass |  | Low | Positive | TS_CHK_011
TC_CHK_007 | Checkout & Payment | Verify comment box accepts text input | User is on checkout page | 1. Proceed to Checkout 2. Click in comment text area 3. Type: 'Please deliver between 9-5 PM' | Comment: Please deliver between 9-5 PM | Text is accepted in comment box without errors | Text accepted in comment box without any errors. | Pass |  | Low | Positive | TS_CHK_011
TC_CHK_008 | Checkout & Payment | Verify 'Place Order' button is visible on checkout page | User is on checkout page | 1. Proceed to Checkout 2. Scroll to bottom or check for Place Order button | Checkout page | 'Place Order' button is visible and enabled | 'Place Order' button visible and enabled on checkout page. | Pass |  | High | Positive | TS_CHK_006
TC_CHK_009 | Checkout & Payment | Verify payment page loads after clicking Place Order | User is on checkout page | 1. Proceed to Checkout 2. Click 'Place Order' 3. Observe navigation | Checkout page loaded | Payment details page loads with card form | Payment page loaded with card input form after clicking Place Order. | Pass |  | High | Positive | TS_CHK_006
TC_CHK_010 | Checkout & Payment | Verify payment form shows Name on Card field | User is on payment page | 1. Proceed to payment page 2. Check for Name on Card field | Payment form | 'Name on Card' input field is visible | 'Name on Card' input field visible on payment form. | Pass |  | High | Positive | TS_CHK_004
TC_CHK_011 | Checkout & Payment | Verify payment form shows Card Number field | User is on payment page | 1. Proceed to payment page 2. Check for Card Number field | Payment form | 'Card Number' input field is visible | 'Card Number' input field visible on payment form. | Pass |  | High | Positive | TS_CHK_004
TC_CHK_012 | Checkout & Payment | Verify payment form shows CVC field | User is on payment page | 1. Proceed to payment page 2. Check for CVC field | Payment form | 'CVC' input field is visible | CVC input field visible on payment form. | Pass |  | High | Positive | TS_CHK_004
TC_CHK_013 | Checkout & Payment | Verify payment form shows Expiry Month field | User is on payment page | 1. Proceed to payment page 2. Check for expiry month field | Payment form | 'Expiration Month' input field is visible | Expiry Month input field visible on payment form. | Pass |  | High | Positive | TS_CHK_004
TC_CHK_014 | Checkout & Payment | Verify payment form shows Expiry Year field | User is on payment page | 1. Proceed to payment page 2. Check for expiry year field | Payment form | 'Expiration Year' input field is visible | Expiry Year input field visible on payment form. | Pass |  | High | Positive | TS_CHK_004
TC_CHK_015 | Checkout & Payment | Verify successful order placement with valid card details | User is on payment page | 1. Enter Name: Kashinath Parmar 2. Card Number: 4111111111111111 3. CVC: 123 4. Month: 12 5. Year: 2027 6. Click 'Pay and Confirm Order' | Name: Kashinath Parmar Card: 4111111111111111 CVC: 123 Exp: 12/2027 | Order placed successfully; confirmation message shown | Order placed successfully. 'Order Placed! Congratulations' message shown. | Pass |  | High | Positive | TS_CHK_006
TC_CHK_016 | Checkout & Payment | Verify order confirmation message shown after placement | User has placed an order successfully | 1. Complete checkout with valid payment 2. Observe the response page | Valid payment details | 'Congratulations! Your order has been confirmed!' message shown | 'Congratulations! Your order has been confirmed!' message displayed. | Pass |  | High | Positive | TS_CHK_007
TC_CHK_017 | Checkout & Payment | Verify checkout fails with empty card name | User is on payment page | 1. Leave Name on Card empty 2. Fill other payment fields 3. Click Pay and Confirm | Name on Card: (blank) | Validation error shown for Name field | No validation error shown for empty Name on Card. Payment attempted without name. | Fail | SE-BUG-007 | High | Negative | TS_CHK_005
TC_CHK_018 | Checkout & Payment | Verify checkout fails with empty card number | User is on payment page | 1. Leave Card Number empty 2. Fill other payment fields 3. Click Pay and Confirm | Card Number: (blank) | Validation error shown for Card Number field | HTML5 validation triggered for empty Card Number field. | Pass |  | High | Negative | TS_CHK_005
TC_CHK_019 | Checkout & Payment | Verify checkout fails with empty CVC field | User is on payment page | 1. Fill Name and Card Number 2. Leave CVC empty 3. Click Pay and Confirm | CVC: (blank) | Validation error shown for CVC field | HTML5 validation triggered for empty CVC field. | Pass |  | High | Negative | TS_CHK_005
TC_CHK_020 | Checkout & Payment | Verify checkout page only accessible to logged-in users | User is NOT logged in | 1. Add product to cart (as guest) 2. Navigate to Cart 3. Click 'Proceed To Checkout' 4. Observe | Guest user (not logged in) | User redirected to login/signup page | Guest user clicking Proceed To Checkout shown a popup with Register/Login option. | Pass |  | High | Security | TS_CHK_010
TC_CHK_021 | Checkout & Payment | Verify checkout page loads within 5 seconds | User proceeds to checkout | 1. Add product to cart 2. Click Proceed To Checkout 3. Measure page load time | Cart with product | Checkout page loads within 5 seconds | Checkout page loaded within 2.5 seconds. | Pass |  | Medium | Performance | NFR_13
TC_CHK_022 | Checkout & Payment | Verify 'Continue On Cart Page' option on checkout popup | Guest user clicks Proceed To Checkout | 1. As guest, add product and click Proceed To Checkout 2. In popup, click 'Continue On Cart Page' | Guest user checkout popup | User returns to Cart page | 'Continue On Cart Page' returns user to the cart page. | Pass |  | Medium | Positive | TS_CHK_001
TC_CHK_023 | Checkout & Payment | Verify 'Register/Login' option on checkout popup for guest | Guest user clicks Proceed To Checkout | 1. As guest, add product and click Proceed To Checkout 2. In popup, click 'Register/Login' | Guest user checkout popup | User redirected to Signup/Login page | Clicking 'Register/Login' redirected user to Signup/Login page. | Pass |  | Medium | Positive | TS_CHK_010
TC_CHK_024 | Checkout & Payment | Verify order review section shows product name correctly | User is on checkout page | 1. Add product 'Blue Top' to cart 2. Proceed to Checkout 3. Check product name in review section | Product: Blue Top | 'Blue Top' shown in order review section | 'Blue Top' correctly shown in the order review section. | Pass |  | High | Positive | TS_CHK_003
TC_CHK_025 | Checkout & Payment | Verify order review section shows product unit price | User is on checkout page | 1. Add product and proceed to checkout 2. Check price per unit in review section | Product with known price | Price per unit displayed correctly in review | Unit price displayed correctly for each product in order review. | Pass |  | High | Positive | TS_CHK_003
TC_CHK_026 | Checkout & Payment | Verify payment page heading text | User is on payment page | 1. Proceed to payment page 2. Check page heading | Payment page | Heading 'Payment' or relevant title is visible | 'Payment' heading visible on the payment page. | Pass |  | Low | Positive | TS_CHK_004
TC_CHK_027 | Checkout & Payment | Verify user registered address matches checkout address | User registered with specific address | 1. Register with address: MG Road, Mumbai 2. Proceed to Checkout 3. Verify displayed address | Registered address: MG Road, Mumbai | Checkout shows MG Road, Mumbai as delivery address | Checkout page showed the registered address correctly. | Pass |  | High | Positive | TS_CHK_002
TC_CHK_028 | Checkout & Payment | Verify payment with card number exceeding digit limit | User is on payment page | 1. Enter card number with 20 digits: 41111111111111111111 2. Click Pay and Confirm | Card Number: 41111111111111111111 (20 digits) | Validation error or payment rejection shown | Payment accepted with 20-digit card number without validation. Order placed. | Fail | SE-BUG-008 | Medium | Boundary | TS_CHK_005
TC_CHK_029 | Checkout & Payment | Verify all payment fields are mandatory | User is on payment page | 1. Leave all payment fields empty 2. Click Pay and Confirm | All fields: (blank) | Validation errors shown for all required fields | HTML5 validation errors shown for all empty payment fields. | Pass |  | High | Negative | TS_CHK_005
TC_CHK_030 | Checkout & Payment | Verify Download Invoice button on order confirmation | User completed a successful order | 1. Complete order placement 2. On confirmation page check for Download Invoice option 3. Click it | Order confirmation page | Invoice downloads successfully as PDF/file | 'Download Invoice' button visible. Invoice downloaded as PDF. | Pass |  | High | Positive | TS_ORD_004
TC_WISH_001 | Wishlist / Recommended Products | Verify recommended products section visible on product detail page | User opens any product detail page | 1. Navigate to any product detail page 2. Scroll to bottom of page 3. Check for 'Recommended items' section | Product detail page | 'Recommended items' section visible with products | 'Recommended items' section visible with multiple products on product detail page. | Pass |  | High | Positive | TS_WISH_001
TC_WISH_002 | Wishlist / Recommended Products | Verify recommended products have name displayed | User is on product detail page with recommendations | 1. Open product detail page 2. Scroll to Recommended items section 3. Observe product names | Recommended items section | Each recommended product shows a name | Product names visible for all recommended items. | Pass |  | Medium | Positive | TS_WISH_006
TC_WISH_003 | Wishlist / Recommended Products | Verify recommended products have price displayed | User is on product detail page with recommendations | 1. Open product detail page 2. Scroll to Recommended items 3. Check for price labels | Recommended items section | Each recommended product shows a price (Rs. value) | Prices with 'Rs.' prefix displayed for each recommended item. | Pass |  | Medium | Positive | TS_WISH_006
TC_WISH_004 | Wishlist / Recommended Products | Verify recommended product can be added to cart | User is on product detail page | 1. Scroll to Recommended items section 2. Click 'Add to cart' for a recommended product 3. Observe confirmation | Recommended product with Add to Cart option | Confirmation modal shown; product added to cart | Confirmation modal shown after clicking Add to cart. Product added. | Pass |  | High | Positive | TS_WISH_002
TC_WISH_005 | Wishlist / Recommended Products | Verify cart count updates after adding recommended product | User adds recommended product to cart | 1. Note cart count before 2. Add recommended product to cart 3. Check cart badge count | Initial cart count noted | Cart badge count increments by 1 | Cart badge count incremented by 1 after adding recommended product. | Pass |  | High | Positive | TS_WISH_003
TC_WISH_006 | Wishlist / Recommended Products | Verify cart page shows recommended product after adding | User added a recommended product | 1. Add recommended product to cart 2. Navigate to Cart page 3. Verify product is listed | Recommended product added | Cart page shows the recommended product with correct details | Cart page showed the recommended product with correct name, price, and quantity. | Pass |  | High | Positive | TS_WISH_003
TC_WISH_007 | Wishlist / Recommended Products | Verify 'Continue Shopping' from add-to-cart modal stays on page | User adds recommended product from detail page | 1. Add recommended product to cart 2. In modal click 'Continue Shopping' | Add-to-cart modal on product page | Modal closes; user stays on product detail page | Modal closed and user remained on product detail page. | Pass |  | Medium | Positive | TS_WISH_004
TC_WISH_008 | Wishlist / Recommended Products | Verify 'View Cart' from add-to-cart modal redirects to cart | User adds recommended product | 1. Add recommended product to cart 2. In modal click 'View Cart' | Add-to-cart modal | User redirected to Shopping Cart page | User redirected to Shopping Cart page after clicking View Cart. | Pass |  | Medium | Positive | TS_WISH_004
TC_WISH_009 | Wishlist / Recommended Products | Verify multiple recommended products can be added to cart | User is on product detail page | 1. Add recommended product 1 and continue shopping 2. Add recommended product 2 3. Navigate to Cart | 2 recommended products added | Both recommended products appear in cart | Both recommended products appeared in cart. | Pass |  | Medium | Positive | TS_WISH_005
TC_WISH_010 | Wishlist / Recommended Products | Verify recommended products image loads correctly | User is on product detail page | 1. Open product detail page 2. Scroll to Recommended items 3. Observe product images | Recommended items section | All recommended product images load without broken icons | All recommended product images loaded without broken icons. | Pass |  | Low | Positive | TS_WISH_008
TC_WISH_011 | Wishlist / Recommended Products | Verify recommended section loads without page errors | User opens product detail page | 1. Open product detail page 2. Open browser console 3. Check for JS errors in console 4. Scroll to Recommended items | Browser console open | No JS errors related to recommended section | No JS errors found in console related to recommended items section. | Pass |  | Medium | Positive | TS_WISH_007
TC_WISH_012 | Wishlist / Recommended Products | Verify recommended section shows at least 1 product | User on product detail page | 1. Open any product detail page 2. Scroll to Recommended items section 3. Count products | Product detail page | At least 1 recommended product is displayed | At least 4 recommended products displayed on the product detail page. | Pass |  | Medium | Positive | TS_WISH_001
TC_WISH_013 | Wishlist / Recommended Products | Verify clicking recommended product opens its detail page | User is on product detail page | 1. Scroll to Recommended items 2. Click on a recommended product name/image 3. Observe navigation | Recommended product available | Recommended product detail page opens | Clicking recommended product image/name opened that product's detail page. | Pass |  | Medium | Positive | TS_WISH_001
TC_WISH_014 | Wishlist / Recommended Products | Verify cart total increases after adding recommended product | User has existing items in cart | 1. Note current cart total (e.g., Rs.500) 2. Add a recommended product (Rs.300) 3. Check new total | Initial total: Rs.500 Recommended product: Rs.300 | Cart total updates to Rs.800 | Cart total updated to include the recommended product price. | Pass |  | High | Positive | TS_WISH_003
TC_WISH_015 | Wishlist / Recommended Products | Verify recommended product has 'Add to cart' button | User is on product detail page recommendations section | 1. Open product detail page 2. Scroll to Recommended items 3. Look for Add to cart buttons | Recommended items section | 'Add to cart' button visible for each recommended product | 'Add to cart' button visible for each recommended product. | Pass |  | High | Positive | TS_WISH_002
TC_WISH_016 | Wishlist / Recommended Products | Verify recommended items section heading text | User is on product detail page | 1. Open product detail page 2. Scroll down 3. Check heading of recommendations section | Product detail page | Heading reads 'Recommended items' or equivalent | Section heading reads 'Recommended items'. | Pass |  | Low | Positive | TS_WISH_001
TC_WISH_017 | Wishlist / Recommended Products | Verify adding recommended product does not remove existing cart items | User has items in cart | 1. Add Product A to cart (existing item) 2. On product page add recommended Product B 3. Navigate to Cart | Cart has Product A; add recommended Product B | Cart shows both Product A and Product B | Both products (existing + recommended) visible in cart after addition. | Pass |  | High | Positive | TS_WISH_003
TC_WISH_018 | Wishlist / Recommended Products | Verify recommended products are different from current product | User is on product detail page | 1. Open product page for 'Blue Top' 2. Scroll to Recommended items 3. Check if recommended items differ | Current product: Blue Top | Recommended items are different products from 'Blue Top' | Recommended items are different products from the currently viewed product. | Pass |  | Medium | Positive | TS_WISH_001
TC_WISH_019 | Wishlist / Recommended Products | Verify recommended products section on multiple product pages | User tests 2 different product pages | 1. Open product 1 detail page 2. Check recommended section 3. Open product 2 detail page 4. Check recommended section | 2 different product detail pages | Both pages have 'Recommended items' section with products | Both product pages had 'Recommended items' section with products. | Pass |  | Low | Positive | TS_WISH_007
TC_WISH_020 | Wishlist / Recommended Products | Verify recommended product price displayed with currency symbol | User on product detail page recommendations | 1. Scroll to Recommended items 2. Check price format for each product | Recommended items section | Prices displayed with Rs. or equivalent currency prefix | Prices for recommended items displayed with 'Rs.' currency prefix. | Pass |  | Low | Positive | TS_WISH_006
TC_ORD_001 | Order Management | Verify order is generated after successful checkout | User completes full checkout flow | 1. Add product to cart 2. Complete checkout with valid payment 3. Note order confirmation | Valid credentials and payment | Order confirmation page shown; order created successfully | Order generated after checkout. Order confirmation page displayed. | Pass |  | High | Positive | TS_ORD_001
TC_ORD_002 | Order Management | Verify order confirmation page shows order success message | User has just placed an order | 1. Complete order placement 2. Observe confirmation page message | Successful order placement | 'Congratulations! Your order has been confirmed!' message visible | 'Congratulations! Your order has been confirmed!' message visible. | Pass |  | High | Positive | TS_ORD_002
TC_ORD_003 | Order Management | Verify order confirmation page shows ordered product(s) | User has placed an order with 1 product | 1. Place order with 'Blue Top' 2. Observe confirmation page product list | Order with Blue Top | Blue Top listed on order confirmation page | Ordered product 'Blue Top' listed on order confirmation page. | Pass |  | High | Positive | TS_ORD_003
TC_ORD_004 | Order Management | Verify order confirmation shows total amount | User views order confirmation page | 1. Place order for Rs.500 product 2. Check total on confirmation page | Order total: Rs.500 | Total amount Rs.500 displayed on confirmation page | Total amount displayed correctly on order confirmation page. | Pass |  | High | Positive | TS_ORD_003
TC_ORD_005 | Order Management | Verify invoice can be downloaded from order confirmation | User is on order confirmation page | 1. Complete order placement 2. On confirmation page click 'Download Invoice' 3. Observe download | Order confirmation page | Invoice file downloads to local machine | Invoice downloaded successfully from order confirmation page. | Pass |  | High | Positive | TS_ORD_004
TC_ORD_006 | Order Management | Verify downloaded invoice file is not empty | User downloads the order invoice | 1. Download invoice from confirmation page 2. Open the downloaded file 3. Verify content | Downloaded invoice file | Invoice contains order details, not empty/corrupt | Downloaded invoice file opened and contained order details (not empty/corrupt). | Pass |  | High | Positive | TS_ORD_005
TC_ORD_007 | Order Management | Verify order history accessible from account section | User is logged in | 1. Login with credentials 2. Click user account area 3. Navigate to Order History section | Logged in: kashinathparma444@gmail.com | Order History page loads with past orders | Order history section found under account area. Previous orders listed. | Pass |  | Medium | Positive | TS_ORD_006
TC_ORD_008 | Order Management | Verify past orders shown in order history | User has placed at least 1 order previously | 1. Navigate to order history 2. Observe order list | At least 1 previous order | Previous order(s) displayed with order details | Past orders displayed with order details (product, amount). | Pass |  | Medium | Positive | TS_ORD_006
TC_ORD_009 | Order Management | Verify order detail page shows payment method | User views a specific order detail | 1. Navigate to order history 2. Click 'View' on any order 3. Check payment method section | Existing order | Payment method used is displayed on order detail page | Payment method shown on order detail page. | Pass |  | Medium | Positive | TS_ORD_007
TC_ORD_010 | Order Management | Verify order total on confirmation matches checkout total | User places an order | 1. Note checkout total: Rs.800 2. Complete order 3. Check confirmation total | Checkout total: Rs.800 | Confirmation shows Rs.800 total (same as checkout) | Confirmation page total matches checkout total. | Pass |  | High | Positive | TS_ORD_008
TC_ORD_011 | Order Management | Verify order confirmation page has 'Continue' button | User is on order confirmation page | 1. Complete order placement 2. Check for 'Continue' button on confirmation page | Order confirmation page | 'Continue' button visible to navigate away | 'Continue' button visible on order confirmation page. | Pass |  | Medium | Positive | TS_ORD_002
TC_ORD_012 | Order Management | Verify clicking Continue on confirmation redirects to homepage | User is on order confirmation page | 1. Place order successfully 2. Click 'Continue' button on confirmation | Order confirmation page | User redirected to homepage | Clicking 'Continue' redirected user to homepage. | Pass |  | Medium | Positive | TS_ORD_002
TC_ORD_013 | Order Management | Verify order confirmation page shows billing address | User places order with saved address | 1. Complete checkout with saved address 2. On confirmation page check billing address | Order confirmation page | Billing address displayed matches registration address | Billing address displayed on confirmation page matches registration address. | Pass |  | Medium | Positive | TS_ORD_002
TC_ORD_014 | Order Management | Verify order confirmation page shows delivery address | User places order | 1. Complete checkout 2. Check delivery address section on confirmation page | Order confirmation page | Delivery address matches address entered during registration | Delivery address on confirmation matches address entered during registration. | Pass |  | Medium | Positive | TS_ORD_002
TC_ORD_015 | Order Management | Verify order history not accessible to logged-out user | User is not logged in | 1. Ensure user is logged out 2. Try to access order history URL directly | No active session | Redirected to login page | Accessing order history URL without login redirected to homepage, not login page. | Fail | SE-BUG-009 | High | Security | NFR_05
TC_ORD_016 | Order Management | Verify order history for user with no orders shows empty state | Newly registered user with no orders | 1. Login with new account (no orders) 2. Navigate to order history | User with 0 orders | Empty state shown with message like 'No orders found' | No specific empty state message for user with no orders. Section appears blank. | Fail | SE-BUG-010 | Low | Positive | TS_ORD_006
TC_ORD_017 | Order Management | Verify order detail view shows product quantity | User views a specific order detail | 1. Navigate to order history 2. Click to view an order 3. Check quantity column | Order with product(s) | Quantity for each product shown in order detail | Quantity for each product shown in order detail view. | Pass |  | Medium | Positive | TS_ORD_003
TC_ORD_018 | Order Management | Verify order detail shows product unit price | User views order detail page | 1. Navigate to order detail 2. Check unit price for each product | Order detail page | Unit price displayed for each ordered product | Unit price displayed for each product on order detail page. | Pass |  | Medium | Positive | TS_ORD_003
TC_ORD_019 | Order Management | Verify multiple orders displayed in order history | User has placed 2+ orders | 1. Place 2 separate orders 2. Navigate to order history 3. Count orders displayed | 2 placed orders | Both orders displayed in order history list | Both orders displayed in order history list. | Pass |  | Medium | Positive | TS_ORD_006
TC_ORD_020 | Order Management | Verify invoice download button text on confirmation page | User is on order confirmation page | 1. Complete order placement 2. Identify the invoice download button 3. Check button label | Order confirmation page | Button labeled 'Download Invoice' or equivalent is visible | 'Download Invoice' button labeled correctly and visible on confirmation page. | Pass |  | Low | Positive | TS_ORD_004
TC_PROF_001 | User Profile & Account | Verify logged-in user can view account information page | User is logged in | 1. Login with kashinathparma444@gmail.com / admin123 2. Click on 'Logged in as [name]' or account section 3. Navigate to Account Information | Logged in: kashinathparma444@gmail.com | Account information page loads with user details | Account information page loaded. User details visible. | Pass |  | High | Positive | TS_PROF_001
TC_PROF_002 | User Profile & Account | Verify username displayed in navigation after login | User logs in | 1. Login with valid credentials 2. Observe top navigation bar | Email: kashinathparma444@gmail.com, Pwd: admin123 | 'Logged in as Kashinath' text visible in nav | 'Logged in as Kashinath' text visible in top navigation bar after login. | Pass |  | Medium | Positive | TS_PROF_002
TC_PROF_003 | User Profile & Account | Verify account details accessible throughout active session | User is logged in and navigates across pages | 1. Login successfully 2. Navigate to Home, Products, Cart pages 3. Click account area at each step | Active logged-in session | Account accessible from all pages during session | Account section accessible from Home, Products, and Cart pages during active session. | Pass |  | Medium | Positive | TS_PROF_003
TC_PROF_004 | User Profile & Account | Verify user can delete account permanently | User is logged in | 1. Login with valid credentials 2. Navigate to account page 3. Find 'Delete Account' option 4. Click Delete 5. Confirm deletion if prompted | Logged in user | Account deleted; user redirected; confirmation shown | 'Delete Account' button found and clicked. Account deleted successfully. | Pass |  | High | Positive | TS_PROF_004
TC_PROF_005 | User Profile & Account | Verify redirect after account deletion | User has just deleted their account | 1. Delete account 2. Observe redirect destination | Post-deletion state | User redirected to appropriate page (homepage or registration) | After deletion, user redirected to 'Account Deleted' confirmation page. | Pass |  | Medium | Positive | TS_PROF_005
TC_PROF_006 | User Profile & Account | Verify deleted account cannot login again | User has deleted their account | 1. After deleting account, navigate to Login 2. Enter deleted credentials: kashinathparma444@gmail.com / admin123 3. Click Login | Deleted account credentials | Error message: account not found OR email/password incorrect | Login with deleted account credentials shows 'Your email or password is incorrect!' | Pass |  | High | Security | TS_PROF_006
TC_PROF_007 | User Profile & Account | Verify account information shows correct registered name | User registered with name 'Kashinath Parmar' | 1. Login 2. Navigate to Account Information 3. Check name field | Registered name: Kashinath Parmar | Name shown as 'Kashinath Parmar' on account page | Account information page shows 'Kashinath Parmar' as registered name. | Pass |  | Medium | Positive | TS_PROF_007
TC_PROF_008 | User Profile & Account | Verify account information shows correct email | User is on account information page | 1. Login 2. Navigate to Account Information 3. Check email field | Registered email: kashinathparma444@gmail.com | Email shows kashinathparma444@gmail.com | Email field shows kashinathparma444@gmail.com on account info page. | Pass |  | Medium | Positive | TS_PROF_007
TC_PROF_009 | User Profile & Account | Verify account page not accessible after logout | User logs out | 1. Login, then Logout 2. Try accessing account URL directly | Logged out state | Redirected to login page (not showing account info) | After logout, accessing account URL redirected to login page. | Pass |  | Medium | Security | TS_PROF_008
TC_PROF_010 | User Profile & Account | Verify account page shows registered address | User registered with address details | 1. Login 2. Navigate to Account Information 3. Check address section | Registered address on record | Address details (street, city, country) visible | Address details (street, city, country) visible on account information page. | Pass |  | Medium | Positive | TS_PROF_007
TC_PROF_011 | User Profile & Account | Verify logged in user name appears consistently across pages | User is logged in and browses multiple pages | 1. Login 2. Visit Home, Products, Cart pages 3. Check username in nav on each page | Logged in user | Username displayed consistently on all visited pages | Username 'Logged in as Kashinath' shown consistently on all visited pages. | Pass |  | Medium | Positive | TS_PROF_003
TC_PROF_012 | User Profile & Account | Verify 'Delete Account' confirmation page text | User initiates account deletion | 1. Login 2. Navigate to Delete Account 3. Check page message | Delete account page | Appropriate confirmation message shown (e.g., 'Account Deleted') | 'Account Deleted!' confirmation message shown after deletion. | Pass |  | Low | Positive | TS_PROF_005
TC_PROF_013 | User Profile & Account | Verify Signup/Login button not visible when logged in | User is logged in | 1. Login with valid credentials 2. Check navigation bar for Signup/Login option | Logged in state | Signup/Login button not visible; Logout button visible instead | Signup/Login option not visible when logged in. Logout button shown instead. | Pass |  | Medium | Positive | TS_PROF_002
TC_PROF_014 | User Profile & Account | Verify Logout option visible when logged in | User is logged in | 1. Login with valid credentials 2. Check navigation bar for Logout option | Logged in state | 'Logout' option visible in nav bar | 'Logout' option visible in navigation bar when user is logged in. | Pass |  | High | Positive | TS_AUTH_010
TC_PROF_015 | User Profile & Account | Verify account information page shows date of birth | User registered with DOB | 1. Login 2. Navigate to Account Information 3. Check DOB field | DOB entered during registration | Date of birth displayed on account information page | Date of birth displayed on account information page. | Pass |  | Low | Positive | TS_PROF_007
TC_PROF_016 | User Profile & Account | Verify mobile number on account information page | User registered with mobile number | 1. Login 2. Navigate to Account Information 3. Check mobile number | Mobile: entered during registration | Mobile number displayed correctly | Mobile number displayed correctly on account information page. | Pass |  | Low | Positive | TS_PROF_007
TC_PROF_017 | User Profile & Account | Verify account title (Mr/Mrs) displayed on account page | User selected title during registration | 1. Login 2. Navigate to Account Information 3. Check title | Title selected during registration (e.g., Mr.) | Title displayed correctly (e.g., Mr.) | Title (Mr.) displayed on account information page. | Pass |  | Low | Positive | TS_PROF_007
TC_PROF_018 | User Profile & Account | Verify user state/province on account page | User registered with state details | 1. Login 2. Navigate to Account Information 3. Check State field | State entered during registration | State value displayed correctly on account page | State/province value shown correctly on account page. | Pass |  | Low | Positive | TS_PROF_007
TC_PROF_019 | User Profile & Account | Verify country on account information page | User registered with country as India | 1. Login 2. Navigate to Account Information 3. Check Country field | Country: India | 'India' displayed in Country field | 'India' displayed in Country field on account information page. | Pass |  | Low | Positive | TS_PROF_007
TC_PROF_020 | User Profile & Account | Verify zipcode on account information page | User registered with zipcode | 1. Login 2. Navigate to Account Information 3. Check Zipcode field | Zipcode entered during registration | Zipcode displayed correctly on account page | Zipcode displayed correctly on account information page. | Pass |  | Low | Positive | TS_PROF_007
TC_CONT_001 | Contact Us & Subscription | Verify Contact Us page accessible from navigation | User is on homepage | 1. On homepage look for 'Contact Us' link in navigation or footer 2. Click it 3. Observe page | Homepage loaded | Contact Us page loads successfully | Contact Us page loaded successfully from navigation link. | Pass |  | Medium | Positive | TS_CONT_001
TC_CONT_002 | Contact Us & Subscription | Verify Contact Us page heading text | User is on Contact Us page | 1. Navigate to Contact Us page 2. Check for page heading | Contact Us page | Heading 'GET IN TOUCH' or 'Contact Us' is displayed | 'GET IN TOUCH' heading displayed on Contact Us page. | Pass |  | Low | Positive | TS_CONT_001
TC_CONT_003 | Contact Us & Subscription | Verify Contact Us form shows Name field | User is on Contact Us page | 1. Navigate to Contact Us page 2. Check for Name input field | Contact Us page | Name input field is visible | Name input field visible on Contact Us page. | Pass |  | Medium | Positive | TS_CONT_002
TC_CONT_004 | Contact Us & Subscription | Verify Contact Us form shows Email field | User is on Contact Us page | 1. Navigate to Contact Us page 2. Check for Email input field | Contact Us page | Email input field is visible | Email input field visible on Contact Us page. | Pass |  | Medium | Positive | TS_CONT_002
TC_CONT_005 | Contact Us & Subscription | Verify Contact Us form shows Subject field | User is on Contact Us page | 1. Navigate to Contact Us page 2. Check for Subject input field | Contact Us page | Subject input field is visible | Subject input field visible on Contact Us page. | Pass |  | Medium | Positive | TS_CONT_002
TC_CONT_006 | Contact Us & Subscription | Verify Contact Us form shows Message/Description field | User is on Contact Us page | 1. Navigate to Contact Us page 2. Check for Message textarea | Contact Us page | Message textarea is visible | Message textarea visible on Contact Us page. | Pass |  | Medium | Positive | TS_CONT_002
TC_CONT_007 | Contact Us & Subscription | Verify successful Contact Us form submission with valid data | User is on Contact Us page | 1. Enter Name: Kashinath Parmar 2. Email: kashinathparma444@gmail.com 3. Subject: Test Query 4. Message: This is a test message 5. Click Submit | Name: Kashinath Parmar Email: kashinathparma444@gmail.com Subject: Test Query | Success message displayed after submission | Success message displayed after form submission with valid data. | Pass |  | High | Positive | TS_CONT_002
TC_CONT_008 | Contact Us & Subscription | Verify Contact Us form fails with empty Name | User is on Contact Us page | 1. Leave Name empty 2. Fill Email, Subject, Message 3. Click Submit | Name: (blank) | Validation error for empty Name field | Browser validation shown for empty Name field. | Pass |  | Medium | Negative | TS_CONT_003
TC_CONT_009 | Contact Us & Subscription | Verify Contact Us form fails with empty Email | User is on Contact Us page | 1. Fill Name 2. Leave Email empty 3. Fill Subject and Message 4. Click Submit | Email: (blank) | Validation error for empty Email field | Browser validation shown for empty Email field. | Pass |  | Medium | Negative | TS_CONT_003
TC_CONT_010 | Contact Us & Subscription | Verify Contact Us form fails with invalid email format | User is on Contact Us page | 1. Enter invalid email: kashinathgmail 2. Fill other fields 3. Click Submit | Email: kashinathgmail | Validation error for invalid email format | Browser validation shown for invalid email format. | Pass |  | Medium | Negative | TS_CONT_003
TC_CONT_011 | Contact Us & Subscription | Verify file upload field is available on Contact Us page | User is on Contact Us page | 1. Navigate to Contact Us page 2. Look for file upload/attachment input | Contact Us page | File upload input field is visible | File upload input field visible on Contact Us page. | Pass |  | Medium | Positive | TS_CONT_004
TC_CONT_012 | Contact Us & Subscription | Verify a valid file can be uploaded through Contact Us form | User is on Contact Us page | 1. Click Choose File button 2. Select a small .txt or .jpg file from local machine 3. Verify file name shown | File: test.txt (small size) | Selected file name displayed next to upload button | Selected file name displayed next to upload button after choosing file. | Pass |  | Medium | Positive | TS_CONT_004
TC_CONT_013 | Contact Us & Subscription | Verify success message text after Contact Us submission | User submits Contact Us form successfully | 1. Fill all Contact Us form fields 2. Click Submit 3. Read success message | Valid form data submitted | Success message like 'Success! Your details have been submitted...' shown | Success message 'Success! Your details have been submitted successfully.' displayed. | Pass |  | High | Positive | TS_CONT_005
TC_CONT_014 | Contact Us & Subscription | Verify Home button visible on Contact Us success page | User has submitted Contact Us form | 1. Submit Contact Us form 2. Check for Home button on success/confirmation page | Post-submission page | 'Home' button is visible | 'Home' button visible on Contact Us success page. | Pass |  | Low | Positive | TS_CONT_005
TC_CONT_015 | Contact Us & Subscription | Verify Home button on Contact Us success redirects to homepage | User has submitted Contact Us form | 1. Submit Contact Us form 2. Click 'Home' button 3. Observe redirect | Contact Us success page | User redirected to homepage | Clicking 'Home' button redirected user to homepage. | Pass |  | Low | Positive | TS_CONT_005
TC_CONT_016 | Contact Us & Subscription | Verify newsletter subscription with valid email | User is on homepage | 1. Locate newsletter subscription section (footer) 2. Enter email: kashinathparma444@gmail.com 3. Click Subscribe/Arrow | Email: kashinathparma444@gmail.com | Success message shown confirming subscription | Success message shown confirming newsletter subscription. | Pass |  | Medium | Positive | TS_CONT_006
TC_CONT_017 | Contact Us & Subscription | Verify newsletter subscription with invalid email format | User is on homepage | 1. Locate newsletter subscription section 2. Enter invalid email: kashinath@ 3. Click Subscribe | Email: kashinath@ (invalid) | Validation error shown for invalid email format | Browser HTML5 validation error shown for invalid email format. | Pass |  | Medium | Negative | TS_CONT_007
TC_CONT_018 | Contact Us & Subscription | Verify newsletter subscription with empty email | User is on homepage | 1. Locate newsletter subscription section 2. Leave email field empty 3. Click Subscribe | Email: (blank) | Validation error or no submission for empty email | Browser validation error for empty email field. | Pass |  | Medium | Negative | TS_CONT_007
TC_CONT_019 | Contact Us & Subscription | Verify newsletter subscription success message text | User subscribes with valid email | 1. Subscribe with valid email 2. Read success message text | Valid email subscribed | Message reads 'You have been successfully subscribed!' or equivalent | Success message 'You have been successfully subscribed!' shown. | Pass |  | Medium | Positive | TS_CONT_008
TC_CONT_020 | Contact Us & Subscription | Verify Contact Us form all fields empty submission fails | User is on Contact Us page | 1. Leave all form fields empty 2. Click Submit | All fields: (blank) | Validation errors shown; form not submitted | Browser validation errors shown for empty fields. Form not submitted. | Pass |  | Medium | Negative | TS_CONT_003

## DEFECT REPORT
Defect ID | Title | Module | Linked TC ID | Environment | Severity | Priority | Steps to Reproduce | Expected Result | Actual Result | Status | Attachments | Reported By | Remarks
SE-BUG-001 | [Auth] No minimum password length validation on registration form | User Registration & Authentication | TC_AUTH_022 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Medium | P2 | 1. Navigate to https://automationexercise.com/login 2. Click Signup, enter name & email 3. Click Signup 4. On Account Details page, enter password: "a" (1 char) 5. Fill remaining fields and click Create Account | Validation error shown: Password must be at least X characters long | Account created successfully with 1-character password. No length validation present. | Open | screenshot_SE-BUG-001.png | Kashinath Parmar | Security risk — weak password allowed
SE-BUG-002 | [Auth] Browser back button restores session after logout (cached page) | User Registration & Authentication | TC_AUTH_027 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | High | P1 | 1. Login with valid credentials 2. Click Logout from navigation 3. Confirm redirect to Login page 4. Click browser Back button | User remains logged out. Protected page not accessible via back navigation. | Browser back button shows cached authenticated page. User appears logged in but session is invalid. | Open | screenshot_SE-BUG-002.png | Kashinath Parmar | Security defect — session not properly invalidated on back navigation
SE-BUG-003 | [Auth] Login fails with uppercase email even for registered user (case-sensitive email) | User Registration & Authentication | TC_AUTH_029 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Medium | P2 | 1. Register with email: kashinathparma444@gmail.com 2. Navigate to Login page 3. Enter email: KASHINATHPARMA444@GMAIL.COM 4. Enter correct password: admin123 5. Click Login | Login succeeds. Email comparison should be case-insensitive per RFC 5321. | Login fails with error: "Your email or password is incorrect!" Email treated as case-sensitive. | Open | screenshot_SE-BUG-003.png | Kashinath Parmar | Usability defect — email addresses are case-insensitive per standard
SE-BUG-004 | [Auth] Mobile number field accepts non-numeric / alphabetic input without validation | User Registration & Authentication | TC_AUTH_030 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Medium | P3 | 1. Go to registration and proceed to address section 2. In Mobile Number field enter: "abcdef" 3. Complete remaining fields 4. Click Create Account | Validation error: Mobile number must be numeric only. | Account created with non-numeric mobile number "abcdef". No validation triggered. | Open | screenshot_SE-BUG-004.png | Kashinath Parmar | Data integrity issue — invalid phone number stored in system
SE-BUG-005 | [Product] No "No Results Found" message when search returns empty results | Product Catalogue & Search | TC_PROD_011 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Low | P3 | 1. Navigate to https://automationexercise.com/products 2. Enter keyword: xyznonexistent123 3. Click Submit button 4. Observe the results area | Appropriate message shown: "No products found for your search" or equivalent. | Page shows "SEARCHED PRODUCTS" heading with empty content below. No message indicating no results found. | Open | screenshot_SE-BUG-005.png | Kashinath Parmar | UX defect — confusing empty state without user feedback
SE-BUG-006 | [Cart] Cart badge count does not update after removing product from cart | Shopping Cart | TC_CART_030 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Medium | P2 | 1. Add 2 different products to cart 2. Verify cart badge shows 2 3. Navigate to Cart page 4. Click X to remove one product 5. Observe cart badge count in navigation | Cart badge count decreases from 2 to 1 after removing one product. | Cart badge count remains at 2 even after product is removed. Badge only updates after page refresh. | Open | screenshot_SE-BUG-006.png | Kashinath Parmar | Real-time update missing — requires page reload to reflect changes
SE-BUG-007 | [Checkout] Payment accepted without Name on Card field — no validation | Checkout & Payment | TC_CHK_017 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | High | P1 | 1. Add product to cart and proceed to checkout 2. Click Place Order to reach payment page 3. Leave "Name on Card" field empty 4. Fill Card Number: 4111111111111111, CVC: 123, Month: 12, Year: 2027 5. Click "Pay and Confirm Order" | Validation error shown: Name on Card is required. | Payment is processed without Name on Card. Order placed successfully with empty name field. | Open | screenshot_SE-BUG-007.png | Kashinath Parmar | Critical payment flow — mandatory field bypass possible
SE-BUG-008 | [Checkout] Payment form accepts card number exceeding 16 digits without validation error | Checkout & Payment | TC_CHK_028 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Medium | P2 | 1. Proceed to payment page 2. Enter card number: 41111111111111111111 (20 digits) 3. Fill other fields with valid data 4. Click Pay and Confirm Order | Validation error shown: Card number must be 16 digits. | Payment accepted with 20-digit card number. Order placed with no validation error. | Open | screenshot_SE-BUG-008.png | Kashinath Parmar | Boundary value failure — no card number length validation
SE-BUG-009 | [Order] Accessing order history URL without login redirects to homepage instead of login page | Order Management | TC_ORD_015 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | High | P1 | 1. Ensure user is logged out 2. Directly navigate to order history URL 3. Observe redirect destination | User redirected to login page with message to authenticate. | User redirected to homepage silently. No login prompt shown. User may not understand why they cannot access orders. | Open | screenshot_SE-BUG-009.png | Kashinath Parmar | Security + UX — should redirect to login with return URL parameter
SE-BUG-010 | [Order] No empty state message shown in order history for user with no orders | Order Management | TC_ORD_016 | Chrome 124 ¦ Windows 11 ¦ automationexercise.com ¦ Build v2.0 | Low | P4 | 1. Register a new account (no orders placed) 2. Login with the new account 3. Navigate to order history section | Empty state message displayed: "No orders found" or "You have not placed any orders yet." | Order history section appears completely blank with no message or placeholder. | Open | screenshot_SE-BUG-010.png | Kashinath Parmar | UX issue — blank page is confusing for new users
DEFECT SUMMARY
Total Defects | 10
Critical | 0
High | 3
Medium | 5
Low | 2
Open | 10
Pass Rate | 190/200 (95%)
Fail Count | 10